## Report
2026-10-16 | 2026-10-18 | 2026-10-16 18:00 | 0 | 1 | [5 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
EWR CULVERTS REPLACEMENT PHASE 2
POSSESSION PROGRESS REPORT - PLANNED vs ACTUAL
Culvert Replacement – Shutdown 03
REPORT GENERATED |  |  | Friday 16-Oct-2026 18:00 prepared by SAR IPMC – Planning
POSSESSION WINDOW |  |  | Friday 16-Oct-2026 00:00 to Sunday 18-Oct-2026 00:00 = 48.0 hours
ELAPSED / REMAINING |  |  | 18.0 h elapsed 30.0 h remaining
SUMMARY - ALL LOCATIONS
Location |  | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Actual % | Buffer to Hand-back |  | 0: PROGRESS 0 - 100% coloured bar = actual % black line = DATA DATE
C263 – KM 209+025 (1 cell) |  | AT RISK | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 39.22% | 2.941% | -19
C265 – KM 210+525 (3 cells) |  | AT RISK | 2026-10-17 22:00 | 2026-10-18 16:00 | 18 | 41.67% | 4.167% | -16
C267 – KM 212+400 (3 cells) |  | AT RISK | 2026-10-17 15:00 | 2026-10-18 09:00 | 18 | 48.78% | 0.6098% | -9
C288 – KM 337+391 (3 cells) |  | AT RISK | 2026-10-17 23:00 | 2026-10-18 17:00 | 18 | 38.3% | 0% | -17
C289 – KM 338+491 (3 cells) |  | AT RISK | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 39.22% | 0% | -19
ALL LOCATIONS |  | AT RISK | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 41.44% | 1.544% | -19
SITE LAYOUT - SCHEMATIC OVERVIEW
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C263 - KM 209+025 - 1 CELL - TSO OTMP / Station 29
1 cell ACTUAL 3% PLANNED 39% PLAN FINISH Sun 18-Oct 01:00 | [9 empty] | 0: AT RISK FORECAST Sun 18-Oct 19:00 18.0 h LATE
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back |  | 0: FRI 16-OCT 00:00 TO SAT 17-OCT 00:00; 24: SAT 17-OCT 00:00 TO SUN 18-OCT 00:00
[10 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00 | [5 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00
1 | OTMP moves from station 29 to Main Line 1 | Completed - Delayed | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 100% | 100% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | 0 | 2 | 3 | 2026-10-16 | 2026-10-16 02:00 | 1 | 1 | -999 | 2
2 | Track removal & panel evacuation (Line 1) | In Progress - BEHIND | 2026-10-16 02:00 | 2026-10-16 18:30 | 16.5 | 100% | 50% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | 2 | 18 | 5 | 2026-10-16 02:00 |  | 50% | 16.5 | 18 | 18.5
3 | Track removal & panel evacuation (Line 3) | ! CHECK DATES | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -24 | 18 | 5 | 2026-10-15 |  | 0 | 18 | 18 | 19
4 | Ballast removal | ! CHECK DATES | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  | 2026-10-16 05:00 | 0 | 18 | 19 | 20
5 | Cutting & removal around existing culvert | NOT STARTED - LATE | 2026-10-16 05:00 | 2026-10-16 23:00 | 18 | 100% | 0% |  | P | [48 empty] | 2 | 5 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 20 | 23
6 | Demolition of existing culvert | NOT STARTED - LATE | 2026-10-16 09:00 | 2026-10-17 03:00 | 18 | 100% | 0% |  | P | [48 empty] | 5 | 9 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 23 | 27
7 | Surface preparation for precast installation | NOT STARTED - LATE | 2026-10-16 11:00 | 2026-10-17 05:00 | 18 | 100% | 0% |  | P | [48 empty] | 9 | 11 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 27 | 29
8 | Installation of new precast culvert | NOT STARTED - LATE | 2026-10-16 16:00 | 2026-10-17 10:00 | 18 | 100% | 0% |  | P | [48 empty] | 11 | 16 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 29 | 34
9 | Apply sealant to the culvert | NOT STARTED - LATE | 2026-10-16 18:00 | 2026-10-17 12:00 | 18 | 100% | 0% |  | P | [48 empty] | 16 | 18 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 34 | 36
10 | Backfill around culvert to subgrade level | NOT STARTED - LATE | 2026-10-16 23:00 | 2026-10-17 17:00 | 18 | 0% | 0% |  | P | [48 empty] | 18 | 23 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 36 | 41
11 | Backfill Subgrade | Not Started | 2026-10-17 01:00 | 2026-10-17 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 23 | 25 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 41 | 43
12 | First layer of ballast (Line 1) | Not Started | 2026-10-17 02:00 | 2026-10-17 20:00 | 18 | 0% | 0% |  | P | [48 empty] | 25 | 26 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 43 | 44
13 | First layer of ballast (Line 3) | Not Started | 2026-10-17 03:00 | 2026-10-17 21:00 | 18 | 0% | 0% |  | P | [48 empty] | 26 | 27 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 44 | 45
14 | Track installation (Line 1) | Not Started | 2026-10-17 04:00 | 2026-10-17 22:00 | 18 | 0% | 0% |  | P | [48 empty] | 27 | 28 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 45 | 46
15 | Track installation (Line 3) | Not Started | 2026-10-17 05:00 | 2026-10-17 23:00 | 18 | 0% | 0% |  | P | [48 empty] | 28 | 29 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 46 | 47
16 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 06:00 | 2026-10-18 | 18 | 0% | 0% |  | P | [48 empty] | 29 | 30 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 47 | 48
17 | Final Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 07:00 | 2026-10-18 01:00 | 18 | 0% | 0% |  | P | [48 empty] | 30 | 31 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 48 | 49
18 | OTMP moves from line 1 to Line 3 TK 121+000 | Not Started | 2026-10-17 08:00 | 2026-10-18 02:00 | 18 | 0% | 0% |  | P | [48 empty] | 31 | 32 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 49 | 50
19 | ATW – 2U (out of destressing) (Line 1) | Not Started | 2026-10-17 10:00 | 2026-10-18 04:00 | 18 | 0% | 0% |  | P | [48 empty] | 32 | 34 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 50 | 52
20 | ATW – 2U (out of destressing) (Line 3) | Not Started | 2026-10-17 12:00 | 2026-10-18 06:00 | 18 | 0% | 0% |  | P | [48 empty] | 34 | 36 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 52 | 54
21 | 1st & 2nd Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 13:00 | 2026-10-18 07:00 | 18 | 0% | 0% |  | P | [48 empty] | 36 | 37 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 54 | 55
22 | Final Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 14:00 | 2026-10-18 08:00 | 18 | 0% | 0% |  | P | [48 empty] | 37 | 38 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 55 | 56
23 | OTMP back towards station 29 | Not Started | 2026-10-17 16:00 | 2026-10-18 10:00 | 18 | 0% | 0% |  | P | [48 empty] | 38 | 40 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 56 | 58
24 | Destressing (incl. 2 ATW) (Line 1) | Not Started | 2026-10-17 20:00 | 2026-10-18 14:00 | 18 | 0% | 0% |  | P | [48 empty] | 40 | 44 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 58 | 62
25 | Destressing (incl. 2 ATW) (Line 3) | Not Started | 2026-10-18 | 2026-10-18 18:00 | 18 | 0% | 0% |  | P | [48 empty] | 44 | 48 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 62 | 66
26 | Finishing (grinding, stamp, UT, inspection) | Not Started | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 48 | 49 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 66 | 67
TOTAL - C263 – KM 209+025 |  | AT RISK | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 39.22% | 2.941% | -19 |  | 0: TOTAL 51.0 activity hours Possession elapsed 18.0 of 48.0 h Report cut-off Fri 16-Oct 18:00
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C265 - KM 210+525 - 3 CELLS - TSO OTMP / Station 29
3 cells ACTUAL 4% PLANNED 42% PLAN FINISH Sat 17-Oct 22:00 | [9 empty] | 0: AT RISK FORECAST Sun 18-Oct 16:00 18.0 h LATE
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back |  | 0: FRI 16-OCT 00:00 TO SAT 17-OCT 00:00; 24: SAT 17-OCT 00:00 TO SUN 18-OCT 00:00
[10 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00 | [5 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00
1 | OTMP moves from station 29 to Main Line 1 | Completed - Ahead | 2026-10-16 01:00 | 2026-10-16 00:30 | -0.5 | 100% | 100% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | 0 | 0.5 | 2 | 2026-10-16 | 2026-10-16 00:30 | 1 | -0.5 | -999 | 0.5
2 | Track removal & panel evacuation (Line 1) | Completed | 2026-10-16 02:00 | 2026-10-16 01:30 | -0.5 | 100% | 100% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 100% | -0.5 | -999 | 1.5
3 | Track removal & panel evacuation (Line 3) | NOT STARTED - LATE | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 18 | 19
4 | Ballast removal | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 19 | 20
5 | Cutting & removal around existing culvert | NOT STARTED - LATE | 2026-10-16 04:00 | 2026-10-16 22:00 | 18 | 100% | 0% |  | P | [48 empty] | 2 | 4 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 20 | 22
6 | Demolition of existing culvert | NOT STARTED - LATE | 2026-10-16 06:00 | 2026-10-17 | 18 | 100% | 0% |  | P | [48 empty] | 4 | 6 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 22 | 24
7 | Surface preparation for precast installation | NOT STARTED - LATE | 2026-10-16 08:00 | 2026-10-17 02:00 | 18 | 100% | 0% |  | P | [48 empty] | 6 | 8 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 24 | 26
8 | Installation of new precast culvert | NOT STARTED - LATE | 2026-10-16 11:00 | 2026-10-17 05:00 | 18 | 100% | 0% |  | P | [48 empty] | 8 | 11 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 26 | 29
9 | Apply sealant to the culvert | NOT STARTED - LATE | 2026-10-16 12:00 | 2026-10-17 06:00 | 18 | 100% | 0% |  | P | [48 empty] | 11 | 12 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 29 | 30
10 | Backfill around culvert to subgrade level | NOT STARTED - LATE | 2026-10-16 15:00 | 2026-10-17 09:00 | 18 | 100% | 0% |  | P | [48 empty] | 12 | 15 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 30 | 33
11 | Backfill Subgrade | NOT STARTED - LATE | 2026-10-16 16:00 | 2026-10-17 10:00 | 18 | 100% | 0% |  | P | [48 empty] | 15 | 16 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 33 | 34
12 | First layer of ballast (Line 1) | NOT STARTED - LATE | 2026-10-16 17:00 | 2026-10-17 11:00 | 18 | 100% | 0% |  | P | [48 empty] | 16 | 17 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 34 | 35
13 | First layer of ballast (Line 3) | NOT STARTED - LATE | 2026-10-16 18:00 | 2026-10-17 12:00 | 18 | 100% | 0% |  | P | [48 empty] | 17 | 18 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 35 | 36
14 | Track installation (Line 1) | NOT STARTED - LATE | 2026-10-16 19:00 | 2026-10-17 13:00 | 18 | 0% | 0% |  | P | [48 empty] | 18 | 19 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 36 | 37
15 | Track installation (Line 3) | Not Started | 2026-10-16 20:00 | 2026-10-17 14:00 | 18 | 0% | 0% |  | P | [48 empty] | 19 | 20 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 37 | 38
16 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-16 21:00 | 2026-10-17 15:00 | 18 | 0% | 0% |  | P | [48 empty] | 20 | 21 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 38 | 39
17 | Final Ballasting / Tamping (Line 1) | Not Started | 2026-10-16 22:00 | 2026-10-17 16:00 | 18 | 0% | 0% |  | P | [48 empty] | 21 | 22 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 39 | 40
18 | OTMP moves from line 1 to Line 3 TK 121+000 | Not Started | 2026-10-16 23:00 | 2026-10-17 17:00 | 18 | 0% | 0% |  | P | [48 empty] | 22 | 23 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 40 | 41
19 | ATW – 2U (out of destressing) (Line 1) | Not Started | 2026-10-17 01:00 | 2026-10-17 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 23 | 25 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 41 | 43
20 | ATW – 2U (out of destressing) (Line 3) | Not Started | 2026-10-17 03:00 | 2026-10-17 21:00 | 18 | 0% | 0% |  | P | [48 empty] | 25 | 27 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 43 | 45
21 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 04:00 | 2026-10-17 22:00 | 18 | 0% | 0% |  | P | [48 empty] | 27 | 28 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 45 | 46
22 | Final Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 05:00 | 2026-10-17 23:00 | 18 | 0% | 0% |  | P | [48 empty] | 28 | 29 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 46 | 47
23 | OTMP back towards station 29 | Not Started | 2026-10-17 07:00 | 2026-10-18 01:00 | 18 | 0% | 0% |  | P | [48 empty] | 29 | 31 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 47 | 49
24 | Destressing (incl. 2 ATW) (Line 1) | Not Started | 2026-10-17 11:00 | 2026-10-18 05:00 | 18 | 0% | 0% |  | P | [48 empty] | 31 | 35 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 49 | 53
25 | Destressing (incl. 2 ATW) (Line 3) | Not Started | 2026-10-17 15:00 | 2026-10-18 09:00 | 18 | 0% | 0% |  | P | [48 empty] | 35 | 39 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 53 | 57
26 | Finishing (grinding, stamp, UT, inspection) | Not Started | 2026-10-17 22:00 | 2026-10-18 16:00 | 18 | 0% | 0% |  | P | [48 empty] | 39 | 46 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 57 | 64
TOTAL - C265 – KM 210+525 |  | AT RISK | 2026-10-17 22:00 | 2026-10-18 16:00 | 18 | 41.67% | 4.167% | -16 |  | 0: TOTAL 48.0 activity hours Possession elapsed 18.0 of 48.0 h Report cut-off Fri 16-Oct 18:00
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C267 - KM 212+400 - 3 CELLS - TSO OTMP / Station 29
3 cells ACTUAL 1% PLANNED 49% PLAN FINISH Sat 17-Oct 15:00 | [9 empty] | 0: AT RISK FORECAST Sun 18-Oct 09:00 18.0 h LATE
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back |  | 0: FRI 16-OCT 00:00 TO SAT 17-OCT 00:00; 24: SAT 17-OCT 00:00 TO SUN 18-OCT 00:00
[10 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00 | [5 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00
1 | OTMP moves from station 29 to main Line 1 | In Progress - BEHIND | 2026-10-16 01:00 | 2026-10-16 18:48 | 17.8 | 100% | 25% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | 0 | 18 | 5 | 2026-10-16 |  | 25% | 17.8 | 18 | 18.8
2 | Track removal & panel evacuation (Line 1) | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 19:48 | 17.8 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 17.8 | 18.8 | 19.8
3 | Track removal & panel evacuation (Line 3) | In Progress - BEHIND | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | 10 | 18 | 5 | 2026-10-16 10:00 |  | 0 | 18 | 18 | 19
4 | Ballast removal | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 19 | 20
5 | Cutting & removal around existing culvert | NOT STARTED - LATE | 2026-10-16 03:00 | 2026-10-16 21:00 | 18 | 100% | 0% |  | P | [48 empty] | 2 | 3 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 20 | 21
6 | Demolition of existing culvert | NOT STARTED - LATE | 2026-10-16 05:00 | 2026-10-16 23:00 | 18 | 100% | 0% |  | P | [48 empty] | 3 | 5 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 21 | 23
7 | Surface preparation for precast installation | NOT STARTED - LATE | 2026-10-16 07:00 | 2026-10-17 01:00 | 18 | 100% | 0% |  | P | [48 empty] | 5 | 7 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 23 | 25
8 | Installation of new precast culvert | NOT STARTED - LATE | 2026-10-16 10:00 | 2026-10-17 04:00 | 18 | 100% | 0% |  | P | [48 empty] | 7 | 10 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 25 | 28
9 | Apply sealant to the culvert | NOT STARTED - LATE | 2026-10-16 11:00 | 2026-10-17 05:00 | 18 | 100% | 0% |  | P | [48 empty] | 10 | 11 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 28 | 29
10 | Backfill around culvert to subgrade level | NOT STARTED - LATE | 2026-10-16 14:00 | 2026-10-17 08:00 | 18 | 100% | 0% |  | P | [48 empty] | 11 | 14 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 29 | 32
11 | Backfill Subgrade | NOT STARTED - LATE | 2026-10-16 15:00 | 2026-10-17 09:00 | 18 | 100% | 0% |  | P | [48 empty] | 14 | 15 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 32 | 33
12 | First layer of ballast (Line 1) | NOT STARTED - LATE | 2026-10-16 16:00 | 2026-10-17 10:00 | 18 | 100% | 0% |  | P | [48 empty] | 15 | 16 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 33 | 34
13 | First layer of ballast (Line 3) | NOT STARTED - LATE | 2026-10-16 17:00 | 2026-10-17 11:00 | 18 | 100% | 0% |  | P | [48 empty] | 16 | 17 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 34 | 35
14 | Track installation (Line 1) | NOT STARTED - LATE | 2026-10-16 18:00 | 2026-10-17 12:00 | 18 | 100% | 0% |  | P | [48 empty] | 17 | 18 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 35 | 36
15 | Track installation (Line 3) | NOT STARTED - LATE | 2026-10-16 19:00 | 2026-10-17 13:00 | 18 | 0% | 0% |  | P | [48 empty] | 18 | 19 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 36 | 37
16 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-16 20:00 | 2026-10-17 14:00 | 18 | 0% | 0% |  | P | [48 empty] | 19 | 20 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 37 | 38
17 | Final Ballasting / Tamping (Line 1) | Not Started | 2026-10-16 21:00 | 2026-10-17 15:00 | 18 | 0% | 0% |  | P | [48 empty] | 20 | 21 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 38 | 39
18 | OTMP moves from line 1 to Line 3 | Not Started | 2026-10-16 22:00 | 2026-10-17 16:00 | 18 | 0% | 0% |  | P | [48 empty] | 21 | 22 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 39 | 40
19 | ATW – 4U (out of destressing) (Line 1) | Not Started | 2026-10-17 | 2026-10-17 18:00 | 18 | 0% | 0% |  | P | [48 empty] | 22 | 24 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 40 | 42
20 | ATW – 4U (out of destressing) (Line 3) | Not Started | 2026-10-17 02:00 | 2026-10-17 20:00 | 18 | 0% | 0% |  | P | [48 empty] | 24 | 26 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 42 | 44
21 | 1st & 2nd Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 03:00 | 2026-10-17 21:00 | 18 | 0% | 0% |  | P | [48 empty] | 26 | 27 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 44 | 45
22 | Final Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 04:00 | 2026-10-17 22:00 | 18 | 0% | 0% |  | P | [48 empty] | 27 | 28 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 45 | 46
23 | OTMP back towards station 29 | Not Started | 2026-10-17 06:00 | 2026-10-18 | 18 | 0% | 0% |  | P | [48 empty] | 28 | 30 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 46 | 48
24 | Destressing (incl. 2 ATW) (Line 1) | Not Started | 2026-10-17 10:00 | 2026-10-18 04:00 | 18 | 0% | 0% |  | P | [48 empty] | 30 | 34 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 48 | 52
25 | Destressing (incl. 2 ATW) (Line 3) | Not Started | 2026-10-17 14:00 | 2026-10-18 08:00 | 18 | 0% | 0% |  | P | [48 empty] | 34 | 38 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 52 | 56
26 | Finishing (grinding, stamp, UT, inspection) | Not Started | 2026-10-17 15:00 | 2026-10-18 09:00 | 18 | 0% | 0% |  | P | [48 empty] | 38 | 39 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 56 | 57
TOTAL - C267 – KM 212+400 |  | AT RISK | 2026-10-17 15:00 | 2026-10-18 09:00 | 18 | 48.78% | 0.6098% | -9 |  | 0: TOTAL 41.0 activity hours Possession elapsed 18.0 of 48.0 h Report cut-off Fri 16-Oct 18:00
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C288 - KM 337+391 - 3 CELLS - SABATCO OTMP / Station 35
3 cells ACTUAL 0% PLANNED 38% PLAN FINISH Sat 17-Oct 23:00 | [9 empty] | 0: AT RISK FORECAST Sun 18-Oct 17:00 18.0 h LATE
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back |  | 0: FRI 16-OCT 00:00 TO SAT 17-OCT 00:00; 24: SAT 17-OCT 00:00 TO SUN 18-OCT 00:00
[10 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00 | [5 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00
1 | OTMP moves from station 35 to main Line 1 | NOT STARTED - LATE | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 18 | 19
2 | Track removal & panel evacuation (Line 1) | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 19 | 20
3 | Track removal & panel evacuation (Line 2) | NOT STARTED - LATE | 2026-10-16 03:00 | 2026-10-16 21:00 | 18 | 100% | 0% |  | P | [48 empty] | 2 | 3 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 20 | 21
4 | Ballast removal | NOT STARTED - LATE | 2026-10-16 04:00 | 2026-10-16 22:00 | 18 | 100% | 0% |  | P | [48 empty] | 3 | 4 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 21 | 22
5 | Cutting & removal around existing culvert | NOT STARTED - LATE | 2026-10-16 05:00 | 2026-10-16 23:00 | 18 | 100% | 0% |  | P | [48 empty] | 4 | 5 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 22 | 23
6 | Demolition of existing culvert | NOT STARTED - LATE | 2026-10-16 07:00 | 2026-10-17 01:00 | 18 | 100% | 0% |  | P | [48 empty] | 5 | 7 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 23 | 25
7 | Surface preparation for precast installation | NOT STARTED - LATE | 2026-10-16 09:00 | 2026-10-17 03:00 | 18 | 100% | 0% |  | P | [48 empty] | 7 | 9 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 25 | 27
8 | Installation of new precast culvert | NOT STARTED - LATE | 2026-10-16 12:00 | 2026-10-17 06:00 | 18 | 100% | 0% |  | P | [48 empty] | 9 | 12 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 27 | 30
9 | Apply sealant to the culvert | NOT STARTED - LATE | 2026-10-16 14:00 | 2026-10-17 08:00 | 18 | 100% | 0% |  | P | [48 empty] | 12 | 14 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 30 | 32
10 | Backfill around culvert to subgrade level | NOT STARTED - LATE | 2026-10-16 17:00 | 2026-10-17 11:00 | 18 | 100% | 0% |  | P | [48 empty] | 14 | 17 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 32 | 35
11 | Backfill Subgrade | NOT STARTED - LATE | 2026-10-16 19:00 | 2026-10-17 13:00 | 18 | 50% | 0% |  | P | [48 empty] | 17 | 19 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 35 | 37
12 | First layer of ballast (Line 1) | Not Started | 2026-10-16 20:00 | 2026-10-17 14:00 | 18 | 0% | 0% |  | P | [48 empty] | 19 | 20 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 37 | 38
13 | First layer of ballast (Line 3) | Not Started | 2026-10-16 21:00 | 2026-10-17 15:00 | 18 | 0% | 0% |  | P | [48 empty] | 20 | 21 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 38 | 39
14 | Track installation (Line 1) | Not Started | 2026-10-16 22:00 | 2026-10-17 16:00 | 18 | 0% | 0% |  | P | [48 empty] | 21 | 22 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 39 | 40
15 | Track installation (Line 3) | Not Started | 2026-10-16 23:00 | 2026-10-17 17:00 | 18 | 0% | 0% |  | P | [48 empty] | 22 | 23 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 40 | 41
16 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 | 2026-10-17 18:00 | 18 | 0% | 0% |  | P | [48 empty] | 23 | 24 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 41 | 42
17 | Final Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 01:00 | 2026-10-17 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 24 | 25 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 42 | 43
18 | OTMP moves from line 1 to line 3 (passing by Station 33) | Not Started | 2026-10-17 03:00 | 2026-10-17 21:00 | 18 | 0% | 0% |  | P | [48 empty] | 25 | 27 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 43 | 45
19 | ATW – 2U (out of destressing) (Line 1) | Not Started | 2026-10-17 05:00 | 2026-10-17 23:00 | 18 | 0% | 0% |  | P | [48 empty] | 27 | 29 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 45 | 47
20 | ATW – 2U (out of destressing) (Line 3) | Not Started | 2026-10-17 07:00 | 2026-10-18 01:00 | 18 | 0% | 0% |  | P | [48 empty] | 29 | 31 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 47 | 49
21 | 1st & 2nd Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 08:00 | 2026-10-18 02:00 | 18 | 0% | 0% |  | P | [48 empty] | 31 | 32 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 49 | 50
22 | Final Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 09:00 | 2026-10-18 03:00 | 18 | 0% | 0% |  | P | [48 empty] | 32 | 33 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 50 | 51
23 | OTMP Back towards station 35 | Not Started | 2026-10-17 11:00 | 2026-10-18 05:00 | 18 | 0% | 0% |  | P | [48 empty] | 33 | 35 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 51 | 53
24 | Destressing (incl. 2 ATW) (Line 1) | Not Started | 2026-10-17 15:00 | 2026-10-18 09:00 | 18 | 0% | 0% |  | P | [48 empty] | 35 | 39 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 53 | 57
25 | Destressing (incl. 2 ATW) (Line 3) | Not Started | 2026-10-17 19:00 | 2026-10-18 13:00 | 18 | 0% | 0% |  | P | [48 empty] | 39 | 43 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 57 | 61
26 | Finishing (grinding, stamp, UT, inspection) | Not Started | 2026-10-17 23:00 | 2026-10-18 17:00 | 18 | 0% | 0% |  | P | [48 empty] | 43 | 47 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 61 | 65
TOTAL - C288 – KM 337+391 |  | AT RISK | 2026-10-17 23:00 | 2026-10-18 17:00 | 18 | 38.3% | 0% | -17 |  | 0: TOTAL 47.0 activity hours Possession elapsed 18.0 of 48.0 h Report cut-off Fri 16-Oct 18:00
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C289 - KM 338+491 - 3 CELLS - SABATCO OTMP / Station 35
3 cells ACTUAL 0% PLANNED 39% PLAN FINISH Sun 18-Oct 01:00 | [9 empty] | 0: AT RISK FORECAST Sun 18-Oct 19:00 18.0 h LATE
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back |  | 0: FRI 16-OCT 00:00 TO SAT 17-OCT 00:00; 24: SAT 17-OCT 00:00 TO SUN 18-OCT 00:00
[10 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00 | [5 empty] | 00:00 - 06:00 | [5 empty] | 06:00 - 12:00 | [5 empty] | 12:00 - 18:00 | [5 empty] | 18:00 - 00:00
1 | OTMP moves from station 35 to main Line 1 | NOT STARTED - LATE | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 18 | 19
2 | Track removal & panel evacuation (Line 1) | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 19 | 20
3 | Track removal & panel evacuation (Line 3) | NOT STARTED - LATE | 2026-10-16 01:00 | 2026-10-16 19:00 | 18 | 100% | 0% |  | P | [48 empty] | 0 | 1 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 18 | 19
4 | Ballast removal | NOT STARTED - LATE | 2026-10-16 02:00 | 2026-10-16 20:00 | 18 | 100% | 0% |  | P | [48 empty] | 1 | 2 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 19 | 20
5 | Cutting & removal around existing culvert | NOT STARTED - LATE | 2026-10-16 04:00 | 2026-10-16 22:00 | 18 | 100% | 0% |  | P | [48 empty] | 2 | 4 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 20 | 22
6 | Demolition of existing culvert | NOT STARTED - LATE | 2026-10-16 08:00 | 2026-10-17 02:00 | 18 | 100% | 0% |  | P | [48 empty] | 4 | 8 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 22 | 26
7 | Surface preparation for precast installation | NOT STARTED - LATE | 2026-10-16 10:00 | 2026-10-17 04:00 | 18 | 100% | 0% |  | P | [48 empty] | 8 | 10 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 26 | 28
8 | Installation of new precast culvert | NOT STARTED - LATE | 2026-10-16 12:00 | 2026-10-17 06:00 | 18 | 100% | 0% |  | P | [48 empty] | 10 | 12 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 28 | 30
9 | Apply sealant to the culvert | NOT STARTED - LATE | 2026-10-16 14:00 | 2026-10-17 08:00 | 18 | 100% | 0% |  | P | [48 empty] | 12 | 14 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 30 | 32
10 | Backfill around culvert to subgrade level | NOT STARTED - LATE | 2026-10-16 19:00 | 2026-10-17 13:00 | 18 | 80% | 0% |  | P | [48 empty] | 14 | 19 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 32 | 37
11 | Backfill Subgrade | Not Started | 2026-10-16 21:00 | 2026-10-17 15:00 | 18 | 0% | 0% |  | P | [48 empty] | 19 | 21 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 37 | 39
12 | First layer of ballast (Line 1) | Not Started | 2026-10-16 22:00 | 2026-10-17 16:00 | 18 | 0% | 0% |  | P | [48 empty] | 21 | 22 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 39 | 40
13 | First layer of ballast (Line 3) | Not Started | 2026-10-16 23:00 | 2026-10-17 17:00 | 18 | 0% | 0% |  | P | [48 empty] | 22 | 23 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 40 | 41
14 | Track installation (Line 1) | Not Started | 2026-10-17 | 2026-10-17 18:00 | 18 | 0% | 0% |  | P | [48 empty] | 23 | 24 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 41 | 42
15 | Track installation (Line 3) | Not Started | 2026-10-17 01:00 | 2026-10-17 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 24 | 25 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 42 | 43
16 | 1st & 2nd Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 02:00 | 2026-10-17 20:00 | 18 | 0% | 0% |  | P | [48 empty] | 25 | 26 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 43 | 44
17 | Final Ballasting / Tamping (Line 1) | Not Started | 2026-10-17 03:00 | 2026-10-17 21:00 | 18 | 0% | 0% |  | P | [48 empty] | 26 | 27 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 44 | 45
18 | OTMP moves from line 1 to line 3 (passing by Station 33) | Not Started | 2026-10-17 05:00 | 2026-10-17 23:00 | 18 | 0% | 0% |  | P | [48 empty] | 27 | 29 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 45 | 47
19 | ATW – 2U (out of destressing) (Line 1) | Not Started | 2026-10-17 07:00 | 2026-10-18 01:00 | 18 | 0% | 0% |  | P | [48 empty] | 29 | 31 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 47 | 49
20 | ATW – 2U (out of destressing) (Line 3) | Not Started | 2026-10-17 09:00 | 2026-10-18 03:00 | 18 | 0% | 0% |  | P | [48 empty] | 31 | 33 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 49 | 51
21 | 1st & 2nd Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 10:00 | 2026-10-18 04:00 | 18 | 0% | 0% |  | P | [48 empty] | 33 | 34 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 51 | 52
22 | Final Ballasting / Tamping (Line 3) | Not Started | 2026-10-17 11:00 | 2026-10-18 05:00 | 18 | 0% | 0% |  | P | [48 empty] | 34 | 35 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 52 | 53
23 | OTMP Back towards station 35 | Not Started | 2026-10-17 13:00 | 2026-10-18 07:00 | 18 | 0% | 0% |  | P | [48 empty] | 35 | 37 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 53 | 55
24 | Destressing (incl. 2 ATW) (Line 1) | Not Started | 2026-10-17 17:00 | 2026-10-18 11:00 | 18 | 0% | 0% |  | P | [48 empty] | 37 | 41 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 55 | 59
25 | Destressing (incl. 2 ATW) (Line 3) | Not Started | 2026-10-17 21:00 | 2026-10-18 15:00 | 18 | 0% | 0% |  | P | [48 empty] | 41 | 45 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 59 | 63
26 | Finishing (grinding, stamp, UT, inspection) | Not Started | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 0% | 0% |  | P | [48 empty] | 45 | 49 | 1 |  |  |  |  | -999 | -999
[9 empty] | A | [48 empty] | -999 | -999 | 0 |  |  | 0 | 18 | 63 | 67
TOTAL - C289 – KM 338+491 |  | AT RISK | 2026-10-18 01:00 | 2026-10-18 19:00 | 18 | 39.22% | 0% | -19 |  | 0: TOTAL 51.0 activity hours Possession elapsed 18.0 of 48.0 h Report cut-off Fri 16-Oct 18:00
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
Formulas:
Planned Finish = MAX(D13:[Planned Finish, row above])
Forecast Finish = MAX(E13:[Forecast Finish, row above])

## Site Layouts
EWR CULVERTS REPLACEMENT PHASE 2 – SHUTDOWN 03 – SITE LAYOUTS
CULVERTS C263 · C265 · C267 – KM 209+025 / 210+525 / 212+400
TSO OTMP stabled at Station 29 (KM 223) before the shutdown, then run out to Main Line 1 and Main Line 3. Hofuf lies to the west, Riyadh to the east.
EWR CULVERTS REPLACEMENT PHASE 2 – SHUTDOWN 03 – SITE LAYOUTS
CULVERTS C288 · C289 – KM 337+391 / 338+491
SABATCO OTMP works Line 1 at both culverts (Phase 1), then transfers to Line 3 via Station 35 (Phase 2). Station 33 lies at KM 309.
Diagrams as supplied with the Shutdown 03 pack. They show OTMP movement phases for each culvert group, not individual culvert cross-sections.

## Data Input
SAR - POSSESSION PROGRESS REPORT ¦ DATA INPUT AND SETTINGS
Everything below drives the report. Yellow cells are yours to edit - every other cell is locked and calculated. | [24 empty] | FS
SS
PROJECT NAME |  | EWR CULVERTS REPLACEMENT PHASE 2 | [5 empty] | REPORT TITLE |  | POSSESSION PROGRESS REPORT - PLANNED vs ACTUAL | [14 empty] | FF
SUBTITLE |  | Culvert Replacement – Shutdown 03 |  |  |  | PREPARED BY |  | SAR IPMC – Planning |  | REPORT CUT-OFF |  | 2026-10-16 18:00 | [12 empty] | SF
POSSESSION WINDOW
WINDOW STARTS |  | 2026-10-16 |  | DURATION |  | 48 |  | UNIT |  | hours | WINDOW ENDS |  | 2026-10-18 | [11 empty] | hours
GANTT STARTS |  | 2026-10-16 |  | GANTT SPAN |  | 48 |  | UNIT |  | hours | ONE COLUMN = |  | 60 min | [11 empty] | days
TOTAL HOURS |  | 48 |  | ELAPSED |  | 18.0 h of 48.0 h |  |  |  | LOCATIONS |  | 5 | ACTIVITIES | 26
The Gantt is always 48 columns wide - a shorter span gives finer columns. Delivered with 5 locations x 26 activities per location; blank an ACTIVITY name to switch that row off.
2026-10-16
LOCATIONS | [24 empty] | 2026-10-17
No | LOCATION NAME | [6 empty] | SCOPE / SUB-TITLE SHOWN ON THE PAGE | [16 empty] | 2026-10-18
1 | C263 – KM 209+025 | [6 empty] | 1 cell │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29 | [16 empty] | 2026-10-19
2 | C265 – KM 210+525 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29 | [16 empty] | 2026-10-20
3 | C267 – KM 212+400 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29
4 | C288 – KM 337+391 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ SABATCO OTMP from Station 35
5 | C289 – KM 338+491 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ SABATCO OTMP from Station 35
LOCATION 1 - C263 – KM 209+025
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
1 | OTMP moves from station 29 to Main Line 1 | 2026-10-16 | 2026-10-16 01:00 | 1 | 0 | FS | 0 | 2026-10-16 | 0:00 | 2026-10-16 | 2:00 | 2 |  | Completed - Delayed |  | 2026-10-16 | 2026-10-16 02:00 | 1 | 1 | 0 | 0 | 2026-10-16 02:00 | 1 | 1 |  | 0
2 | Track removal & panel evacuation (Line 1) | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 1 | FS | 0 | 2026-10-16 | 2:00 |  |  |  | 50% | In Progress - BEHIND |  | 2026-10-16 02:00 |  | 50% | 1 | -0.5 | 0 | 2026-10-16 18:30 | 16.5 | 16.5 |  | 0
3 | Track removal & panel evacuation (Line 3) | 2026-10-16 | 2026-10-16 01:00 | 1 | 1 | SS | 0 | 2026-10-15 | 0:00 |  |  |  |  | ! CHECK DATES |  | 2026-10-15 |  | 0 | 1 | -1 | 1 | 2026-10-16 19:00 | 18 | 18 |  | 0
4 | Ballast removal | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 3 | FS | 0 |  |  | 2026-10-16 | 5:00 |  |  | ! CHECK DATES |  |  | 2026-10-16 05:00 | 0 | 1 | -1 | 1 | 2026-10-16 19:00 | 17 | 18 |  | 0
5 | Cutting & removal around existing culvert | 2026-10-16 02:00 | 2026-10-16 05:00 | 3 | 4 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 16 | 18 |  | 0
6 | Demolition of existing culvert | 2026-10-16 05:00 | 2026-10-16 09:00 | 4 | 5 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -4 | 0 | 2026-10-16 22:00 | 13 | 18 |  | 0
7 | Surface preparation for precast installation | 2026-10-16 09:00 | 2026-10-16 11:00 | 2 | 6 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 9 | 18 |  | 0
8 | Installation of new precast culvert | 2026-10-16 11:00 | 2026-10-16 16:00 | 5 | 7 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -5 | 0 | 2026-10-16 23:00 | 7 | 18 |  | 0
9 | Apply sealant to the culvert | 2026-10-16 16:00 | 2026-10-16 18:00 | 2 | 8 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 2 | 18 |  | 0
10 | Backfill around culvert to subgrade level | 2026-10-16 18:00 | 2026-10-16 23:00 | 5 | 9 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 23:00 | 0 | 18 |  | 0
11 | Backfill Subgrade | 2026-10-16 23:00 | 2026-10-17 01:00 | 2 | 10 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 01:00 | 0 | 18 |  | 0
12 | First layer of ballast (Line 1) | 2026-10-17 01:00 | 2026-10-17 02:00 | 1 | 11 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 02:00 | 0 | 18 |  | 0
13 | First layer of ballast (Line 3) | 2026-10-17 02:00 | 2026-10-17 03:00 | 1 | 12 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 03:00 | 0 | 18 |  | 0
14 | Track installation (Line 1) | 2026-10-17 03:00 | 2026-10-17 04:00 | 1 | 13 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 04:00 | 0 | 18 |  | 0
15 | Track installation (Line 3) | 2026-10-17 04:00 | 2026-10-17 05:00 | 1 | 14 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 05:00 | 0 | 18 |  | 0
16 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-17 05:00 | 2026-10-17 06:00 | 1 | 15 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 06:00 | 0 | 18 |  | 0
17 | Final Ballasting / Tamping (Line 1) | 2026-10-17 06:00 | 2026-10-17 07:00 | 1 | 16 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 07:00 | 0 | 18 |  | 0
18 | OTMP moves from line 1 to Line 3 TK 121+000 | 2026-10-17 07:00 | 2026-10-17 08:00 | 1 | 17 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 08:00 | 0 | 18 |  | 0
19 | ATW – 2U (out of destressing) (Line 1) | 2026-10-17 08:00 | 2026-10-17 10:00 | 2 | 18 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 10:00 | 0 | 18 |  | 0
20 | ATW – 2U (out of destressing) (Line 3) | 2026-10-17 10:00 | 2026-10-17 12:00 | 2 | 19 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 12:00 | 0 | 18 |  | 0
21 | 1st & 2nd Ballasting / Tamping (Line 3) | 2026-10-17 12:00 | 2026-10-17 13:00 | 1 | 20 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 13:00 | 0 | 18 |  | 0
22 | Final Ballasting / Tamping (Line 3) | 2026-10-17 13:00 | 2026-10-17 14:00 | 1 | 21 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 14:00 | 0 | 18 |  | 0
23 | OTMP back towards station 29 | 2026-10-17 14:00 | 2026-10-17 16:00 | 2 | 22 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 16:00 | 0 | 18 |  | 0
24 | Destressing (incl. 2 ATW) (Line 1) | 2026-10-17 16:00 | 2026-10-17 20:00 | 4 | 23 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 20:00 | 0 | 18 |  | 0
25 | Destressing (incl. 2 ATW) (Line 3) | 2026-10-17 20:00 | 2026-10-18 | 4 | 24 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-18 | 0 | 18 |  | 0
26 | Finishing (grinding, stamp, UT, inspection) | 2026-10-18 | 2026-10-18 01:00 | 1 | 25 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-18 01:00 | 0 | 18 |  | 0
TOT | C263 – KM 209+025 - sum of activity hours |  | 2026-10-18 01:00 | 51 | [7 empty] | 2 | 2.941% | BEHIND |  |  |  | 0.029412 | 0.39216 | -0.36275 |  | 2026-10-18 19:00 | 18
LOCATION 2 - C265 – KM 210+525
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
1 | OTMP moves from station 29 to Main Line 1 | 2026-10-16 | 2026-10-16 01:00 | 1 | 0 | FS | 0 | 2026-10-16 | 0:00 | 2026-10-16 | 0:30 | 0.5 |  | Completed - Ahead |  | 2026-10-16 | 2026-10-16 00:30 | 1 | 1 | 0 | 0 | 2026-10-16 00:30 | -0.5 | -0.5 |  | 0
2 | Track removal & panel evacuation (Line 1) | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 1 | FS | 0 | [5 empty] | 100% | Completed |  |  |  | 100% | 1 | 0 | 0 | 2026-10-16 02:00 | 0 | -0.5 |  | 0
3 | Track removal & panel evacuation (Line 3) | 2026-10-16 | 2026-10-16 01:00 | 1 | 1 | SS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 18 | 18 |  | 0
4 | Ballast removal | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 3 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 18 |  | 0
5 | Cutting & removal around existing culvert | 2026-10-16 02:00 | 2026-10-16 04:00 | 2 | 4 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 16 | 18 |  | 0
6 | Demolition of existing culvert | 2026-10-16 04:00 | 2026-10-16 06:00 | 2 | 5 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 14 | 18 |  | 0
7 | Surface preparation for precast installation | 2026-10-16 06:00 | 2026-10-16 08:00 | 2 | 6 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 12 | 18 |  | 0
8 | Installation of new precast culvert | 2026-10-16 08:00 | 2026-10-16 11:00 | 3 | 7 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 10 | 18 |  | 0
9 | Apply sealant to the culvert | 2026-10-16 11:00 | 2026-10-16 12:00 | 1 | 8 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 7 | 18 |  | 0
10 | Backfill around culvert to subgrade level | 2026-10-16 12:00 | 2026-10-16 15:00 | 3 | 9 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 6 | 18 |  | 0
11 | Backfill Subgrade | 2026-10-16 15:00 | 2026-10-16 16:00 | 1 | 10 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 3 | 18 |  | 0
12 | First layer of ballast (Line 1) | 2026-10-16 16:00 | 2026-10-16 17:00 | 1 | 11 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 2 | 18 |  | 0
13 | First layer of ballast (Line 3) | 2026-10-16 17:00 | 2026-10-16 18:00 | 1 | 12 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 1 | 18 |  | 0
14 | Track installation (Line 1) | 2026-10-16 18:00 | 2026-10-16 19:00 | 1 | 13 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 19:00 | 0 | 18 |  | 0
15 | Track installation (Line 3) | 2026-10-16 19:00 | 2026-10-16 20:00 | 1 | 14 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 20:00 | 0 | 18 |  | 0
16 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-16 20:00 | 2026-10-16 21:00 | 1 | 15 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 21:00 | 0 | 18 |  | 0
17 | Final Ballasting / Tamping (Line 1) | 2026-10-16 21:00 | 2026-10-16 22:00 | 1 | 16 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 22:00 | 0 | 18 |  | 0
18 | OTMP moves from line 1 to Line 3 TK 121+000 | 2026-10-16 22:00 | 2026-10-16 23:00 | 1 | 17 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 23:00 | 0 | 18 |  | 0
19 | ATW – 2U (out of destressing) (Line 1) | 2026-10-16 23:00 | 2026-10-17 01:00 | 2 | 18 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 01:00 | 0 | 18 |  | 0
20 | ATW – 2U (out of destressing) (Line 3) | 2026-10-17 01:00 | 2026-10-17 03:00 | 2 | 19 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 03:00 | 0 | 18 |  | 0
21 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-17 03:00 | 2026-10-17 04:00 | 1 | 20 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 04:00 | 0 | 18 |  | 0
22 | Final Ballasting / Tamping (Line 3) | 2026-10-17 04:00 | 2026-10-17 05:00 | 1 | 21 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 05:00 | 0 | 18 |  | 0
23 | OTMP back towards station 29 | 2026-10-17 05:00 | 2026-10-17 07:00 | 2 | 22 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 07:00 | 0 | 18 |  | 0
24 | Destressing (incl. 2 ATW) (Line 1) | 2026-10-17 07:00 | 2026-10-17 11:00 | 4 | 23 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 11:00 | 0 | 18 |  | 0
25 | Destressing (incl. 2 ATW) (Line 3) | 2026-10-17 11:00 | 2026-10-17 15:00 | 4 | 24 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 15:00 | 0 | 18 |  | 0
26 | Finishing (grinding, stamp, UT, inspection) | 2026-10-17 15:00 | 2026-10-17 22:00 | 7 | 25 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 22:00 | 0 | 18 |  | 0
TOT | C265 – KM 210+525 - sum of activity hours |  | 2026-10-17 22:00 | 48 | [7 empty] | 0.5 | 4.167% | BEHIND |  |  |  | 0.041667 | 0.41667 | -0.375 |  | 2026-10-18 16:00 | 18
LOCATION 3 - C267 – KM 212+400
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
1 | OTMP moves from station 29 to main Line 1 | 2026-10-16 | 2026-10-16 01:00 | 1 | 0 | FS | 0 | 2026-10-16 | 0:00 |  |  |  | 25% | In Progress - BEHIND |  | 2026-10-16 |  | 25% | 1 | -0.75 | 0 | 2026-10-16 18:45 | 17.8 | 17.8 |  | 0
2 | Track removal & panel evacuation (Line 1) | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 1 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 17.8 |  | 0
3 | Track removal & panel evacuation (Line 3) | 2026-10-16 | 2026-10-16 01:00 | 1 | 1 | SS | 0 | 2026-10-16 10:00 | 0:00 |  |  |  |  | In Progress - BEHIND |  | 2026-10-16 10:00 |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 18 | 18 |  | 0
4 | Ballast removal | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 3 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 18 |  | 0
5 | Cutting & removal around existing culvert | 2026-10-16 02:00 | 2026-10-16 03:00 | 1 | 4 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 16 | 18 |  | 0
6 | Demolition of existing culvert | 2026-10-16 03:00 | 2026-10-16 05:00 | 2 | 5 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 15 | 18 |  | 0
7 | Surface preparation for precast installation | 2026-10-16 05:00 | 2026-10-16 07:00 | 2 | 6 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 13 | 18 |  | 0
8 | Installation of new precast culvert | 2026-10-16 07:00 | 2026-10-16 10:00 | 3 | 7 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 11 | 18 |  | 0
9 | Apply sealant to the culvert | 2026-10-16 10:00 | 2026-10-16 11:00 | 1 | 8 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 8 | 18 |  | 0
10 | Backfill around culvert to subgrade level | 2026-10-16 11:00 | 2026-10-16 14:00 | 3 | 9 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 7 | 18 |  | 0
11 | Backfill Subgrade | 2026-10-16 14:00 | 2026-10-16 15:00 | 1 | 10 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 4 | 18 |  | 0
12 | First layer of ballast (Line 1) | 2026-10-16 15:00 | 2026-10-16 16:00 | 1 | 11 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 3 | 18 |  | 0
13 | First layer of ballast (Line 3) | 2026-10-16 16:00 | 2026-10-16 17:00 | 1 | 12 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 2 | 18 |  | 0
14 | Track installation (Line 1) | 2026-10-16 17:00 | 2026-10-16 18:00 | 1 | 13 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 1 | 18 |  | 0
15 | Track installation (Line 3) | 2026-10-16 18:00 | 2026-10-16 19:00 | 1 | 14 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 19:00 | 0 | 18 |  | 0
16 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-16 19:00 | 2026-10-16 20:00 | 1 | 15 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 20:00 | 0 | 18 |  | 0
17 | Final Ballasting / Tamping (Line 1) | 2026-10-16 20:00 | 2026-10-16 21:00 | 1 | 16 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 21:00 | 0 | 18 |  | 0
18 | OTMP moves from line 1 to Line 3 | 2026-10-16 21:00 | 2026-10-16 22:00 | 1 | 17 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 22:00 | 0 | 18 |  | 0
19 | ATW – 4U (out of destressing) (Line 1) | 2026-10-16 22:00 | 2026-10-17 | 2 | 18 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 | 0 | 18 |  | 0
20 | ATW – 4U (out of destressing) (Line 3) | 2026-10-17 | 2026-10-17 02:00 | 2 | 19 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 02:00 | 0 | 18 |  | 0
21 | 1st & 2nd Ballasting / Tamping (Line 3) | 2026-10-17 02:00 | 2026-10-17 03:00 | 1 | 20 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 03:00 | 0 | 18 |  | 0
22 | Final Ballasting / Tamping (Line 3) | 2026-10-17 03:00 | 2026-10-17 04:00 | 1 | 21 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 04:00 | 0 | 18 |  | 0
23 | OTMP back towards station 29 | 2026-10-17 04:00 | 2026-10-17 06:00 | 2 | 22 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 06:00 | 0 | 18 |  | 0
24 | Destressing (incl. 2 ATW) (Line 1) | 2026-10-17 06:00 | 2026-10-17 10:00 | 4 | 23 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 10:00 | 0 | 18 |  | 0
25 | Destressing (incl. 2 ATW) (Line 3) | 2026-10-17 10:00 | 2026-10-17 14:00 | 4 | 24 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 14:00 | 0 | 18 |  | 0
26 | Finishing (grinding, stamp, UT, inspection) | 2026-10-17 14:00 | 2026-10-17 15:00 | 1 | 25 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 15:00 | 0 | 18 |  | 0
TOT | C267 – KM 212+400 - sum of activity hours |  | 2026-10-17 15:00 | 41 | [7 empty] | 0 | 0.6098% | BEHIND |  |  |  | 0.0060976 | 0.4878 | -0.48171 |  | 2026-10-18 09:00 | 18
LOCATION 4 - C288 – KM 337+391
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
1 | OTMP moves from station 35 to main Line 1 | 2026-10-16 | 2026-10-16 01:00 | 1 | 0 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 18 | 18 |  | 0
2 | Track removal & panel evacuation (Line 1) | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 1 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 18 |  | 0
3 | Track removal & panel evacuation (Line 2) | 2026-10-16 02:00 | 2026-10-16 03:00 | 1 | 2 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 16 | 18 |  | 0
4 | Ballast removal | 2026-10-16 03:00 | 2026-10-16 04:00 | 1 | 3 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 15 | 18 |  | 0
5 | Cutting & removal around existing culvert | 2026-10-16 04:00 | 2026-10-16 05:00 | 1 | 4 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 14 | 18 |  | 0
6 | Demolition of existing culvert | 2026-10-16 05:00 | 2026-10-16 07:00 | 2 | 5 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 13 | 18 |  | 0
7 | Surface preparation for precast installation | 2026-10-16 07:00 | 2026-10-16 09:00 | 2 | 6 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 11 | 18 |  | 0
8 | Installation of new precast culvert | 2026-10-16 09:00 | 2026-10-16 12:00 | 3 | 7 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 9 | 18 |  | 0
9 | Apply sealant to the culvert | 2026-10-16 12:00 | 2026-10-16 14:00 | 2 | 8 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 6 | 18 |  | 0
10 | Backfill around culvert to subgrade level | 2026-10-16 14:00 | 2026-10-16 17:00 | 3 | 9 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -3 | 0 | 2026-10-16 21:00 | 4 | 18 |  | 0
11 | Backfill Subgrade | 2026-10-16 17:00 | 2026-10-16 19:00 | 2 | 10 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 0.5 | -1 | 0 | 2026-10-16 20:00 | 1 | 18 |  | 0
12 | First layer of ballast (Line 1) | 2026-10-16 19:00 | 2026-10-16 20:00 | 1 | 11 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 20:00 | 0 | 18 |  | 0
13 | First layer of ballast (Line 3) | 2026-10-16 20:00 | 2026-10-16 21:00 | 1 | 12 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 21:00 | 0 | 18 |  | 0
14 | Track installation (Line 1) | 2026-10-16 21:00 | 2026-10-16 22:00 | 1 | 13 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 22:00 | 0 | 18 |  | 0
15 | Track installation (Line 3) | 2026-10-16 22:00 | 2026-10-16 23:00 | 1 | 14 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 23:00 | 0 | 18 |  | 0
16 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-16 23:00 | 2026-10-17 | 1 | 15 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 | 0 | 18 |  | 0
17 | Final Ballasting / Tamping (Line 1) | 2026-10-17 | 2026-10-17 01:00 | 1 | 16 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 01:00 | 0 | 18 |  | 0
18 | OTMP moves from line 1 to line 3 (passing by Station 33) | 2026-10-17 01:00 | 2026-10-17 03:00 | 2 | 17 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 03:00 | 0 | 18 |  | 0
19 | ATW – 2U (out of destressing) (Line 1) | 2026-10-17 03:00 | 2026-10-17 05:00 | 2 | 18 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 05:00 | 0 | 18 |  | 0
20 | ATW – 2U (out of destressing) (Line 3) | 2026-10-17 05:00 | 2026-10-17 07:00 | 2 | 19 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 07:00 | 0 | 18 |  | 0
21 | 1st & 2nd Ballasting / Tamping (Line 3) | 2026-10-17 07:00 | 2026-10-17 08:00 | 1 | 20 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 08:00 | 0 | 18 |  | 0
22 | Final Ballasting / Tamping (Line 3) | 2026-10-17 08:00 | 2026-10-17 09:00 | 1 | 21 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 09:00 | 0 | 18 |  | 0
23 | OTMP Back towards station 35 | 2026-10-17 09:00 | 2026-10-17 11:00 | 2 | 22 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 11:00 | 0 | 18 |  | 0
24 | Destressing (incl. 2 ATW) (Line 1) | 2026-10-17 11:00 | 2026-10-17 15:00 | 4 | 23 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 15:00 | 0 | 18 |  | 0
25 | Destressing (incl. 2 ATW) (Line 3) | 2026-10-17 15:00 | 2026-10-17 19:00 | 4 | 24 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 19:00 | 0 | 18 |  | 0
26 | Finishing (grinding, stamp, UT, inspection) | 2026-10-17 19:00 | 2026-10-17 23:00 | 4 | 25 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 23:00 | 0 | 18 |  | 0
TOT | C288 – KM 337+391 - sum of activity hours |  | 2026-10-17 23:00 | 47 | [7 empty] | 0 | 0% | BEHIND |  |  |  | 0 | 0.38298 | -0.38298 |  | 2026-10-18 17:00 | 18
LOCATION 5 - C289 – KM 338+491
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
1 | OTMP moves from station 35 to main Line 1 | 2026-10-16 | 2026-10-16 01:00 | 1 | 0 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 18 | 18 |  | 0
2 | Track removal & panel evacuation (Line 1) | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 1 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 18 |  | 0
3 | Track removal & panel evacuation (Line 3) | 2026-10-16 | 2026-10-16 01:00 | 1 | 1 | SS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 18 | 18 |  | 0
4 | Ballast removal | 2026-10-16 01:00 | 2026-10-16 02:00 | 1 | 3 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -1 | 0 | 2026-10-16 19:00 | 17 | 18 |  | 0
5 | Cutting & removal around existing culvert | 2026-10-16 02:00 | 2026-10-16 04:00 | 2 | 4 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 16 | 18 |  | 0
6 | Demolition of existing culvert | 2026-10-16 04:00 | 2026-10-16 08:00 | 4 | 5 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -4 | 0 | 2026-10-16 22:00 | 14 | 18 |  | 0
7 | Surface preparation for precast installation | 2026-10-16 08:00 | 2026-10-16 10:00 | 2 | 6 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 10 | 18 |  | 0
8 | Installation of new precast culvert | 2026-10-16 10:00 | 2026-10-16 12:00 | 2 | 7 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 8 | 18 |  | 0
9 | Apply sealant to the culvert | 2026-10-16 12:00 | 2026-10-16 14:00 | 2 | 8 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 1 | -2 | 0 | 2026-10-16 20:00 | 6 | 18 |  | 0
10 | Backfill around culvert to subgrade level | 2026-10-16 14:00 | 2026-10-16 19:00 | 5 | 9 | FS | 0 | [6 empty] | NOT STARTED - LATE |  |  |  | 0 | 0.8 | -4 | 0 | 2026-10-16 23:00 | 4 | 18 |  | 0
11 | Backfill Subgrade | 2026-10-16 19:00 | 2026-10-16 21:00 | 2 | 10 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 21:00 | 0 | 18 |  | 0
12 | First layer of ballast (Line 1) | 2026-10-16 21:00 | 2026-10-16 22:00 | 1 | 11 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 22:00 | 0 | 18 |  | 0
13 | First layer of ballast (Line 3) | 2026-10-16 22:00 | 2026-10-16 23:00 | 1 | 12 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-16 23:00 | 0 | 18 |  | 0
14 | Track installation (Line 1) | 2026-10-16 23:00 | 2026-10-17 | 1 | 13 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 | 0 | 18 |  | 0
15 | Track installation (Line 3) | 2026-10-17 | 2026-10-17 01:00 | 1 | 14 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 01:00 | 0 | 18 |  | 0
16 | 1st & 2nd Ballasting / Tamping (Line 1) | 2026-10-17 01:00 | 2026-10-17 02:00 | 1 | 15 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 02:00 | 0 | 18 |  | 0
17 | Final Ballasting / Tamping (Line 1) | 2026-10-17 02:00 | 2026-10-17 03:00 | 1 | 16 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 03:00 | 0 | 18 |  | 0
18 | OTMP moves from line 1 to line 3 (passing by Station 33) | 2026-10-17 03:00 | 2026-10-17 05:00 | 2 | 17 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 05:00 | 0 | 18 |  | 0
19 | ATW – 2U (out of destressing) (Line 1) | 2026-10-17 05:00 | 2026-10-17 07:00 | 2 | 18 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 07:00 | 0 | 18 |  | 0
20 | ATW – 2U (out of destressing) (Line 3) | 2026-10-17 07:00 | 2026-10-17 09:00 | 2 | 19 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 09:00 | 0 | 18 |  | 0
21 | 1st & 2nd Ballasting / Tamping (Line 3) | 2026-10-17 09:00 | 2026-10-17 10:00 | 1 | 20 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 10:00 | 0 | 18 |  | 0
22 | Final Ballasting / Tamping (Line 3) | 2026-10-17 10:00 | 2026-10-17 11:00 | 1 | 21 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 11:00 | 0 | 18 |  | 0
23 | OTMP Back towards station 35 | 2026-10-17 11:00 | 2026-10-17 13:00 | 2 | 22 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 13:00 | 0 | 18 |  | 0
24 | Destressing (incl. 2 ATW) (Line 1) | 2026-10-17 13:00 | 2026-10-17 17:00 | 4 | 23 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 17:00 | 0 | 18 |  | 0
25 | Destressing (incl. 2 ATW) (Line 3) | 2026-10-17 17:00 | 2026-10-17 21:00 | 4 | 24 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-17 21:00 | 0 | 18 |  | 0
26 | Finishing (grinding, stamp, UT, inspection) | 2026-10-17 21:00 | 2026-10-18 01:00 | 4 | 25 | FS | 0 | [6 empty] | Not Started |  |  |  | 0 | 0 | 0 | 0 | 2026-10-18 01:00 | 0 | 18 |  | 0
TOT | C289 – KM 338+491 - sum of activity hours |  | 2026-10-18 01:00 | 51 | [7 empty] | 0 | 0% | BEHIND |  |  |  | 0 | 0.39216 | -0.39216 |  | 2026-10-18 19:00 | 18
Formulas:
EWR CULVERTS REPLACEMENT PHASE 2 = IF(OR(B27="",1>O10),"",IF([PRED No]=0,C8,IF([PREPARED BY]="SS",OFFSET(C26,[PRED No],0)+[LAG (h)]/24,IF([PREPARED BY]="FF",OFFSET(D26,[PRED No],0)+[LAG (h)]/24-[DUR (h)]/24,IF([PREPARED BY]="SF",OFFSET(C26,[PRED No],0)+[LAG (h)]/24-[DUR (h)]/24,OFFSET(D26,[PRED No],0)+[LAG (h)]/24)))))
Planned Finish = IF(OR(B27="",1>O10),"",[EWR CULVERTS REPLACEMENT PHASE 2]+[DUR (h)]/24)
Planned Finish = IF(COUNT(D27:[Planned Finish, row above])=0,"",MAX(D27:[Planned Finish, row above]))