## Slide 1
Gantt Chart
Project Activity Timeline · Site Suspension and Shoring Works
Background
Phase 1
Phase 2
Phase 3
Milestone
Activity / Milestone
August
September 2026
October 2026
T
27
F
28
S
29
S
30
M
31
T
1
W
2
T
3
F
4
S
5
S
6
M
7
T
8
W
9
T
10
F
11
S
12
S
13
M
14
T
15
W
16
T
17
F
18
S
19
S
20
M
21
T
22
W
23
T
24
F
25
S
26
S
27
M
28
T
29
W
30
T
1
F
2
S
3
S
4
M
5
T
6
W
7
T
8
F
9
S
10
S
11
M
12
T
13
W
14
T
15
F
16
S
17
S
18
M
19
T
20
W
21
T
22
F
23
S
24
1 Background – Permit Request
1.1
31 Aug
Work Permit Requested
28 days
1.2
28 Sep
Permit Request Rejected
+3 days
2 Phase 1 – Suspension & Site Assessment
2.1
1 Oct
Project Activities Suspended
+2 days
2.2
3 Oct
Joint Site Visit
+1 day
2.3
4 Oct
Risk Assessment & Mitigation Plan Submitted
+1 day
2.4
5 Oct
Detailed Action Plan Requested
+2 days
3 Phase 2 – Method Statement Preparation & Review
3.1
7 Oct
Method Statement (MoS) Submitted
3.2
7 Oct
Stakeholders Meeting
+1 day
3.3
8 Oct
Stakeholders’ Clarifications Answered
+3 days
3.4
11 Oct
Engineering Clarification Received
+1 day
3.5
12 Oct
MoS Revision 2 Submitted
+1 day
4 Phase 3 – Work Permit Issuance
4.1
13 Oct
Safety Department Contacted
+1 day
4.2
14 Oct
Permit Circulated for Approvals
+1 day
4.3
15 Oct
Further Department Comments
+4 days
4.4
19 Oct
MoS Revision 3 Submitted
+1 day
4.5
20 Oct
Last Clarification Cleared
+1 day
4.6
21 Oct
Work Permit Ready for Signature