## Cover
SAR |  | SAUDI ARABIA RAILWAYS
Project Controls ¦ East West Railway
EAST WEST RAILWAY (EWR) ¦ CULVERTS REPLACEMENT PHASE 2
SHUTDOWN 02 - PROGRESS REPORT
Culverts C028, C052, C053, C067 and C070 ¦ August 2026
SHUTDOWN START | SHUTDOWN FINISH | PLANNED DURATION | WORK LOCATIONS
21-Aug-2026 | 22-Aug-2026 | 2 days | 5 culverts
00:00 | 00:00 | per activity plan | KM 116+700 - 132+198
NOTE FOR RECONCILIATION
Header finish reads 22-Aug-2026 00:00 while the activity plan runs to 23-Aug-2026.
Waiting locations read TK 121+000 / TK 131+000 here and TK 120+000 / TK 130+000 in the OTMP narrative.
DOCUMENT CONTROL
DOCUMENT REF. | REVISION | DATE | STATUS
PREPARED BY | CHECKED BY | APPROVED BY | CLIENT / SAR
Name / Signature / Date | Name / Signature / Date | Name / Signature / Date | Name / Signature / Date
Culverts Replacement Phase 2 - EWR ¦ Shutdown 02 Progress Report |  | Page 1 of 1 - Cover
SAUDI ARABIA RAILWAYS ¦ SAR.COM.SA

## Shutdown02 Progress
EWR CULVERTS REPLACEMENT PHASE 2 - SHUTDOWN 03 PROGRESS TRACKER
AUGUST 2026 ¦ Culverts: C263, C265, C267, C288, C289
46305.3452 |  | Start : 16-Oct-2026 00.00 AM | [6 empty] | Finish : 17-Oct-2026 00.00 AM |  |  |  |  | Time Remaining : |  |  | 7day15hrs41mins
[19 empty] | 2026-10-16 23:59 | Day 2 (00:00): | 2026-10-17 23:59
2026-10-10 08:17
7day15hrs41mins
No | Work Description | No. Hours | Wt. %P | Wt.%PA |  | Date (Plan) |  | Date (Actual |  | Time (Plan-Target) |  | Total Time (Plan) | Time (vs. Actual) |  | Total Time Completed | Time Difference (Ahead, On-Time, Delayed) | Progress Status | Remarks
[5 empty] | % Progress | Start | End | Start | End | Start | End |  | Start | End
Completed - Ahead of time
LOCATION: C263 , TK 209+025 (Line 1 & Line 3) | [18 empty] | Completed
1 | Pre-Shutdown Arrangement (Mobilization Works) | T-48 Hours | [14 empty] | Not Started |  | Completed - Delayed
2 | TSO OTMP moves from station 29 to Main Line 1 | 0.041667 | 2.03 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
3 | Track removal and evacuation of panels (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 1:00 | 2:00 | 0.041667 |  |  |  |  | Not Started |  | In-progress
4 | Track removal and evacuation of panels (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started
5 | Ballast removal | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started |  | Completed - Ontime
6 | Cutting and removal of material around existing culvert | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 3:00 | 6:00 | 0.125 |  |  |  |  | Not Started
7 | Demolition of existing culvert | 0.16667 | 8.1633 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 6:00 | 10:00 | 0.16667 |  |  |  |  | Not Started
8 | Surface preparation for the precast culvert installation | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 10:00 | 12:00 | 0.083333 |  |  |  |  | Not Started
9 | Installation of new precast culvert | 0.20833 | 10.2041 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 12:00 | 17:00 | 0.20833 |  |  |  |  | Not Started
10 | Apply sealant to the culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 17:00 | 19:00 | 0.083333 |  |  |  |  | Not Started
11 | Backfill around the culvert till subgrade level | 0.20833 | 10.2041 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 19:00 | 24:00 | 0.20833 |  |  |  |  | Not Started
12 | Backfill Subgrade | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 24:00 | 26:00 | 0.083333 |  |  |  |  | Not Started
13 | First layer of ballast (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 26:00 | 27:00 | 0.041667 |  |  |  |  | Not Started
14 | First layer of ballast (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 27:00 | 28:00 | 0.041667 |  |  |  |  | Not Started
15 | Track installation (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 28:00 | 29:00 | 0.041667 |  |  |  |  | Not Started
16 | Track installation (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 29:00 | 30:00 | 0.041667 |  |  |  |  | Not Started
17 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 30:00 | 31:00 | 0.041667 |  |  |  |  | Not Started
18 | Final Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 31:00 | 32:00 | 0.041667 |  |  |  |  | Not Started
19 | TSO OTMP moves from line 1 to Line 3 TK 121+000 | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 32:00 | 33:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
20 | ATW - 2U (out of destressing) (line 1) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 33:00 | 35:00 | 0.083333 |  |  |  |  | Not Started
21 | ATW - 2U (out of destressing) (line 3) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 35:00 | 37:00 | 0.083333 |  |  |  |  | Not Started
22 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 37:00 | 38:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location
23 | Final Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 38:00 | 39:00 | 0.041667 |  |  |  |  | Not Started
24 | TSO Back towards station 29 | 0.083333 |  |  |  | 2026-10-17 | 2026-10-17 |  |  | 39:00 | 38:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
25 | No Work Hours due to tempratare |  |  |  |  | 2026-10-17 | 2026-10-17 | [9 empty] | Not Started | Rest Hours
26 | Destressing (including 2 ATW) (line 1) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 39:00 | 43:00 | 0.16667 |  |  |  |  | Not Started
27 | Destressing (including 2 ATW) (line 3) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 43:00 | 47:00 | 0.16667 |  |  |  |  | Not Started
28 | Finishing (including final grinding, welding stamp, UT, inspection, etc.) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 47:00 | 48:00 | 0.041667 |  |  |  |  | Not Started
|  | 1900-01-01 01:00 | 99.9892 | 0% | Progress
No | Work Description | No. Hours | Wt. %P | Wt.%PA |  | Date (Plan) |  |  | Date of Actual Completion | Time (Plan-Target) |  | Total Time (Plan) | Time (vs. Actual) |  | Total Time Completed | Time Difference (Ahead, On-Time, Delayed) | Progress Status | Remarks
[5 empty] | % Progress | Start | End |  |  | Start | End |  | Start | End
Completed - Ahead of time
LOCATION: C265 ,TK 210+525 (Line 1 & Line 3)
1 | Pre-Shutdown Arrangement (Mobilization Works) | T-48 Hours | [14 empty] | Not Started |  | Completed - Delayed
2 | TSO OTMP moves from station 29 to Main Line 1 | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
3 | Track removal and evacuation of panels (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 1:00 | 2:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location | In-progress
4 | Track removal and evacuation of panels (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started
5 | Ballast removal | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started |  | Completed - Ontime
6 | Cutting and removal of material around existing culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 3:00 | 6:00 | 0.125 |  |  |  |  | Not Started
7 | Demolition of existing culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 6:00 | 10:00 | 0.16667 |  |  |  |  | Not Started
8 | Surface preparation for the precast culvert installation | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 10:00 | 12:00 | 0.083333 |  |  |  |  | Not Started
9 | Installation of new precast culvert | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 12:00 | 15:00 | 0.125 |  |  |  |  | Not Started
10 | Apply sealant to the culvert | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 15:00 | 16:00 | 0.041667 |  |  |  |  | Not Started
11 | Backfill around the culvert till subgrade level | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 16:00 | 19:00 | 0.125 |  |  |  |  | Not Started
12 | Backfill Subgrade | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 19:00 | 20:00 | 0.041667 |  |  |  |  | Not Started
13 | First layer of ballast (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 20:00 | 21:00 | 0.041667 |  |  |  |  | Not Started
14 | First layer of ballast (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 21:00 | 22:00 | 0.041667 |  |  |  |  | Not Started
15 | Track installation (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 22:00 | 23:00 | 0.041667 |  |  |  |  | Not Started
16 | Track installation (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 23:00 | 24:00 | 0.041667 |  |  |  |  | Not Started
17 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started
18 | Final Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 3:00 | 4:00 | 0.041667 |  |  |  |  | Not Started
19 | TSO OTMP moves from line 1 to Line 3 TK 121+000 | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 32:00 | 33:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
20 | ATW - 2U (out of destressing) (line 1) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 24:00 | 26:00 | 0.083333 |  |  |  |  | Not Started
21 | ATW - 2U (out of destressing) (line 3) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 33:00 | 35:00 | 0.083333 |  |  |  |  | Not Started
22 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 35:00 | 36:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location
23 | Final Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 36:00 | 37:00 | 0.041667 |  |  |  |  | Not Started
24 | TSO Back towards station 29 | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 39:00 | 38:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
25 | No Work Hours due to tempratare |  |  |  |  | 2026-10-17 | 2026-10-17 | [9 empty] | Not Started | Rest Hours
26 | Destressing (including 2 ATW) (line 1) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 4:00 | 8:00 | 0.16667 |  |  |  |  | Not Started
27 | Destressing (including 2 ATW) (line 3) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 37:00 | 41:00 | 0.16667 |  |  |  |  | Not Started
28 | Finishing (including final grinding, welding stamp, UT, inspection, etc.) | 0.29167 | 14.2857 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 41:00 | 48:00 | 0.29167 |  |  |  |  | Not Started
|  | 1899-12-31 22:00 | 97.9592 | 0% | Progress
No | Work Description | No. Hours | Wt. %P | Wt.%PA |  | Date (Plan) |  |  | Date of Actual Completion | Time (Plan-Target) |  | Total Time (Plan) | Time (vs. Actual) |  | Total Time Completed | Time Difference (Ahead, On-Time, Delayed) | Progress Status | Remarks
[5 empty] | % Progress | Start | End |  |  | Start | End |  | Start | End
LOCATION: C267 , TK 212+400 (Line 1 & Line 3)
1 | Pre-Shutdown Arrangement (Mobilization Works) | T-48 Hours | [14 empty] | Not Started |  | Completed - Delayed
2 | TSO OTMP moves from station 29 to main Line 1 |  | 2.03 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
3 | Track removal and evacuation of panels (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 1:00 | 2:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location | In-progress
4 | Track removal and evacuation of panels (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started
5 | Ballast removal | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started |  | Completed - Ontime
6 | Cutting and removal of material around existing culvert | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 3:00 | 6:00 | 0.125 |  |  |  |  | Not Started
7 | Demolition of existing culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 6:00 | 10:00 | 0.16667 |  |  |  |  | Not Started
8 | Surface preparation for the precast culvert installation | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 10:00 | 12:00 | 0.083333 |  |  |  |  | Not Started
9 | Installation of new precast culvert | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 12:00 | 15:00 | 0.125 |  |  |  |  | Not Started
10 | Apply sealant to the culvert | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 15:00 | 16:00 | 0.041667 |  |  |  |  | Not Started
11 | Backfill around the culvert till subgrade level | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 16:00 | 19:00 | 0.125 |  |  |  |  | Not Started
12 | Backfill Subgrade | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 19:00 | 20:00 | 0.041667 |  |  |  |  | Not Started
13 | First layer of ballast (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 20:00 | 21:00 | 0.041667 |  |  |  |  | Not Started
14 | First layer of ballast (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 21:00 | 22:00 | 0.041667 |  |  |  |  | Not Started
15 | Track installation (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 22:00 | 23:00 | 0.041667 |  |  |  |  | Not Started
16 | Track installation (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 23:00 | 24:00 | 0.041667 |  |  |  |  | Not Started
17 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 24:00 | 25:00 | 0.041667 |  |  |  |  | Not Started
18 | Final Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 25:00 | 26:00 | 0.041667 |  |  |  |  | Not Started
19 | TSO OTMP moves from line 1 to Line 3 | 0.041667 | 4 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 8:00 | 9:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
20 | ATW - 4U (out of destressing) (line 1) | 0.083333 | 1.3 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 26:00 | 28:00 | 0.083333 |  |  |  |  | Not Started
21 | ATW - 4U (out of destressing) (line 3) | 0.083333 | 1.31 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 9:00 | 11:00 | 0.083333 |  |  |  |  | Not Started
22 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 9:00 | 10:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location
23 | Final Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 10:00 | 11:00 | 0.041667 |  |  |  |  | Not Started
24 | TSO Back towards station 29 | 0.083333 |  |  |  | 2026-10-17 | 2026-10-17 |  |  | 39:00 | 38:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
25 | No Work Hours due to tempratare |  |  |  |  | 2026-10-17 | 2026-10-17 |  |  |  |  | 0 | [5 empty] | Rest Hours
26 | Destressing (including 2 ATW) (line 1) | 0.16667 |  |  |  | 2026-10-17 | 2026-10-17 |  |  | 17:00 | 21:00 | 0.16667
27 | Destressing (including 2 ATW) (line 3) |  |  |  |  | 2026-10-17 | 2026-10-17 |  |  | 21:00 | 21:00 | 0
28 | Finishing (including final grinding, welding stamp, UT, inspection, etc.) | 0.041667 | 2 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 23:00 | 24:00 | 0.041667 |  |  |  |  | Not Started
|  | 1899-12-31 10:00 | 59.6196 | 0% | Progress
No | Work Description | No. Hours | Wt. %P | Wt.%PA |  | Date (Plan) |  | Date (Actual) |  | Time (Plan-Target) |  | Total Time (Plan) | Time (vs. Actual) |  | Total Time Completed | Time Difference (Ahead, On-Time, Delayed) | Progress Status | Remarks
[5 empty] | % Progress | Start | End | Start | End | Start | End |  | Start | End
LOCATION: C288 , TK 337+391 (Line 1 & Line 3)
1 | Pre-Shutdown Arrangement (Mobilization Works) | T-48 Hours | [14 empty] | Not Started |  | Completed - Delayed
2 | SABATCO OTMP moves from station 35 to main Line 1 | 0.041667 | 2.03 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
3 | Track removal and evacuation of panels (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 1:00 | 2:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location | In-progress
4 | Track removal and evacuation of panels (line 2) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started
5 | Ballast removal | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started |  | Completed - Ontime
6 | Cutting and removal of material around existing culvert | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 3:00 | 6:00 | 0.125 |  |  |  |  | Not Started
7 | Demolition of existing culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 6:00 | 10:00 | 0.16667 |  |  |  |  | Not Started
8 | Surface preparation for the precast culvert installation | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 10:00 | 12:00 | 0.083333 |  |  |  |  | Not Started
9 | Installation of new precast culvert | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 12:00 | 15:00 | 0.125 |  |  |  |  | Not Started
10 | Apply sealant to the culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 15:00 | 17:00 | 0.083333 |  |  |  |  | Not Started
11 | Backfill around the culvert till subgrade level | 0.125 | 6.1224 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 17:00 | 20:00 | 0.125 |  |  |  |  | Not Started
12 | Backfill Subgrade | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 20:00 | 22:00 | 0.083333 |  |  |  |  | Not Started
13 | First layer of ballast (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 22:00 | 23:00 | 0.041667 |  |  |  |  | Not Started
14 | First layer of ballast (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 23:00 | 24:00 | 0.041667 |  |  |  |  | Not Started
15 | Track installation (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 24:00 | 25:00 | 0.041667 |  |  |  |  | Not Started
16 | Track installation (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 25:00 | 26:00 | 0.041667 |  |  |  |  | Not Started
17 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 26:00 | 27:00 | 0.041667 |  |  |  |  | Not Started
18 | Final Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 27:00 | 28:00 | 0.041667 |  |  |  |  | Not Started
19 | SABATCO OTMP moves from line 1 to line 3 (passing by Station 33) | 0.083333 | 4 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 6:00 | 8:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
20 | ATW - 2U (out of destressing) (line 1) | 0.083333 | 1.3 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 28:00 | 30:00 | 0.083333 |  |  |  |  | Not Started
21 | ATW - 2U (out of destressing) (line 3) | 0.083333 | 1.31 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 14:00 | 16:00 | 0.083333 |  |  |  |  | Not Started
22 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 8:00 | 9:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location
23 | Final Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 9:00 | 10:00 | 0.041667 |  |  |  |  | Not Started
24 | OTMP Back towards station 35 | 0.083333 |  |  |  | 2026-10-17 | 2026-10-17 |  |  | 36:00 | 38:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
25 | No Work Hours due to tempratare |  |  |  |  | 2026-10-17 | 2026-10-17 |  |  |  |  | 0 |  |  |  |  | Not Started | Rest Hours
26 | Destressing (including 2 ATW) (line 1) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 10:00 | 14:00 | 0.16667 |  |  |  |  | Not Started
27 | Destressing (including 2 ATW) (line 3) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 16:00 | 20:00 | 0.16667 |  |  |  |  | Not Started
28 | Finishing (including final grinding, welding stamp, UT, inspection, etc.) | 0.16667 | 2 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 20:00 | 24:00 | 0.16667 |  |  |  |  | Not Started
|  | 1899-12-31 21:00 | 80.0278 | 0% | Progress
No | Work Description | No. Hours | Wt. %P | Wt.%PA |  | Date (Plan) |  | Date of Actual |  | Time (Plan-Target) |  | Total Time (Plan) | Time (vs. Actual) |  | Total Time Completed | Time Difference (Ahead, On-Time, Delayed) | Progress Status | Remarks
[5 empty] | % Progress | Start | End |  |  | Start | End |  | Start | End
LOCATION: C289 , TK 338+491 (Line 1 & Line 3)
1 | Pre-Shutdown Arrangement (Mobilization Works) | T-48 Hours | [14 empty] | Not Started |  | Completed - Delayed
2 | SABATCO OTMP moves from station 35 to main Line 1 | 0.041667 | 2.03 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started | OTMP Movement
3 | Track removal and evacuation of panels (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 1:00 | 2:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location | In-progress
4 | Track removal and evacuation of panels (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 0:00 | 1:00 | 0.041667 |  |  |  |  | Not Started
5 | Ballast removal | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 2:00 | 3:00 | 0.041667 |  |  |  |  | Not Started |  | Completed - Ontime
6 | Cutting and removal of material around existing culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 3:00 | 5:00 | 0.083333 |  |  |  |  | Not Started
7 | Demolition of existing culvert | 0.16667 | 8.1633 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 5:00 | 9:00 | 0.16667 |  |  |  |  | Not Started
8 | Surface preparation for the precast culvert installation | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 9:00 | 11:00 | 0.083333 |  |  |  |  | Not Started
9 | Installation of new precast culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 11:00 | 13:00 | 0.083333 |  |  |  |  | Not Started
10 | Apply sealant to the culvert | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 13:00 | 15:00 | 0.083333 |  |  |  |  | Not Started
11 | Backfill around the culvert till subgrade level | 0.20833 | 10.2041 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 15:00 | 20:00 | 0.20833 |  |  |  |  | Not Started
12 | Backfill Subgrade | 0.083333 | 4.0816 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 20:00 | 22:00 | 0.083333 |  |  |  |  | Not Started
13 | First layer of ballast (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 22:00 | 23:00 | 0.041667 |  |  |  |  | Not Started
14 | First layer of ballast (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-16 | 2026-10-16 |  |  | 23:00 | 24:00 | 0.041667 |  |  |  |  | Not Started
15 | Track installation (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 24:00 | 25:00 | 0.041667 |  |  |  |  | Not Started
16 | Track installation (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 25:00 | 26:00 | 0.041667 |  |  |  |  | Not Started
17 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 4:00 | 5:00 | 0.041667 |  |  |  |  | Not Started
18 | Final Ballasting/Tamping/Stabilization/Profiling (line 1) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 5:00 | 6:00 | 0.041667 |  |  |  |  | Not Started
19 | SABATCO OTMP moves from line 1 to line 3 (passing by Station 33) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 6:00 | 8:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
21 | ATW - 2U (out of destressing) (line 1) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 26:00 | 28:00 | 0.083333 |  |  |  |  | Not Started
22 | ATW - 2U (out of destressing) (line 3) | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 8:00 | 10:00 | 0.083333 |  |  |  |  | Not Started
23 | First and Second Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 10:00 | 11:00 | 0.041667 |  |  |  |  | Not Started | After OTMP pass to location
24 | Final Ballasting/Tamping/Stabilization/Profiling (line 3) | 0.041667 | 2.0408 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 11:00 | 12:00 | 0.041667 |  |  |  |  | Not Started
25 | OTMP Back towards station 35 | 0.083333 | 4.0816 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 36:00 | 38:00 | 0.083333 |  |  |  |  | Not Started | OTMP Movement
26 | No Work Hours due to tempratare |  |  |  |  | 2026-10-17 | 2026-10-17 |  |  |  |  | 0 |  |  |  |  | Not Started | Rest Hours
27 | Destressing (including 2 ATW) (line 1) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 0:00 | 4:00 | 0.16667 |  |  |  |  | Not Started
28 | Destressing (including 2 ATW) (line 3) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 4:00 | 8:00 | 0.16667 |  |  |  |  | Not Started
29 | Finishing (including final grinding, welding stamp, UT, inspection, etc.) | 0.16667 | 8.1633 | 0 |  | 2026-10-17 | 2026-10-17 |  |  | 8:00 | 12:00 | 0.16667 |  |  |  |  | Not Started
|  | 1900-01-01 01:00 | 104.0708 | 0% | Progress
Formulas:
No. Hours = SUM(C20:[No. Hours, row above])-C42
Total Time (Plan) = [End]-[Time (Plan-Target)]
This Date Current Time :

## Charts
Culvert | Total Hrs (Plan) | Completed | Remaining
C028 (116+700) | 0.041667 | 0% | 100%
C052 (124+415) | 0.29167 | 0% | 100%
C053 (124+585) | 0.041667 | 0% | 100%
C067 (129+103) | 0.16667 | 0% | 100%
C070 (132+198) | 0.16667 | 0% | 100%
OVERALL | 0.70833 | 0% | 100%
DURATION COMPLETION BY CULVERT