## Slide 1
UFWL Project – Timeline
Project Activity Timeline · Site Suspension and Shoring Works
Background – Permit Request
Phase 1 – Suspension & Site Assessment
Phase 2 – Method Statement Preparation & Review
Phase 3 – Work Permit Issuance
1
Mon 31 Aug 2026
Background – Permit Request
Work Permit Requested
2
Mon 28 Sep 2026
Background – Permit Request
Permit Request Rejected
3
Thu 1 Oct 2026
Phase 1 – Suspension & Site Assessment
Project Activities Suspended
4
Sat 3 Oct 2026
Phase 1 – Suspension & Site Assessment
Joint Site Visit
5
Sun 4 Oct 2026
Phase 1 – Suspension & Site Assessment
Risk Assessment & Mitigation Plan Submitted
6
Mon 5 Oct 2026
Phase 1 – Suspension & Site Assessment
Detailed Action Plan Requested
7
Wed 7 Oct 2026
Phase 2 – Method Statement Preparation & Review
Method Statement (MoS) Submitted
8
Wed 7 Oct 2026
Phase 2 – Method Statement Preparation & Review
Stakeholders Meeting
9
Thu 8 Oct 2026
Phase 2 – Method Statement Preparation & Review
Stakeholders’ Clarifications Answered
10
Sun 11 Oct 2026
Phase 2 – Method Statement Preparation & Review
Engineering Clarification Received
11
Mon 12 Oct 2026
Phase 2 – Method Statement Preparation & Review
MoS Revision 2 Submitted
12
Tue 13 Oct 2026
Phase 3 – Work Permit Issuance
Safety Department Contacted
13
Wed 14 Oct 2026
Phase 3 – Work Permit Issuance
Permit Circulated for Approvals
14
Thu 15 Oct 2026
Phase 3 – Work Permit Issuance
Further Department Comments
15
Mon 19 Oct 2026
Phase 3 – Work Permit Issuance
MoS Revision 3 Submitted
16
Tue 20 Oct 2026
Phase 3 – Work Permit Issuance
Last Clarification Cleared
17
Wed 21 Oct 2026
Phase 3 – Work Permit Issuance
Work Permit Ready for Signature