## Slide 1
UFWL Project – Timeline
Project Activity Timeline · Site Suspension and Shoring Works
Background – Permit Request
Phase 1 – Suspension & Site Assessment
Phase 2 – Method Statement Preparation & Review
Phase 3 – Work Permit Issuance
1
Mon 31 Aug 2026
Background – Permit Request
Work Permit Requested
2
Mon 28 Sep 2026
Background – Permit Request
Permit Request Rejected
3
Thu 1 Oct 2026
Phase 1 – Suspension & Site Assessment
Project Activities Suspended
4
Sat 3 Oct 2026
Phase 1 – Suspension & Site Assessment
Joint Site Visit
5
Sun 4 Oct 2026
Phase 1 – Suspension & Site Assessment
Risk Assessment & Mitigation Plan Submitted
6
Mon 5 Oct 2026
Phase 1 – Suspension & Site Assessment
Detailed Action Plan Requested
7
Wed 7 Oct 2026
Phase 2 – Method Statement Preparation & Review
Method Statement (MoS) Submitted
8
Wed 7 Oct 2026
Phase 2 – Method Statement Preparation & Review
Stakeholders Meeting
9
Thu 8 Oct 2026
Phase 2 – Method Statement Preparation & Review
Stakeholders’ Clarifications Answered
10
Sun 11 Oct 2026
Phase 2 – Method Statement Preparation & Review
Engineering Clarification Received
11
Mon 12 Oct 2026
Phase 2 – Method Statement Preparation & Review
MoS Revision 2 Submitted
12
Tue 13 Oct 2026
Phase 3 – Work Permit Issuance
Safety Department Contacted
13
Wed 14 Oct 2026
Phase 3 – Work Permit Issuance
Permit Circulated for Approvals
14
Thu 15 Oct 2026
Phase 3 – Work Permit Issuance
Further Department Comments
15
Mon 19 Oct 2026
Phase 3 – Work Permit Issuance
MoS Revision 3 Submitted
16
Tue 20 Oct 2026
Phase 3 – Work Permit Issuance
Last Clarification Cleared
17
Wed 21 Oct 2026
Phase 3 – Work Permit Issuance
Work Permit Ready for Signature

## Slide 2
Remaining Works – Shoring & Pit Works Programme
RYDN-WLB pit works · Proposed by Gulf Development Company for Contracting · Rev 01 · 12 Oct 2026
Critical path
Activity (colour = work group)
Milestone
Non-working day
Status date
→ Dependency (FS / SS)
Sr
Activity
Predecessor
Dur. (wd)
Start
Finish
October 2026
November 2026
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
S
10
S
11
M
12
T
13
W
14
T
15
F
16
S
17
S
18
M
19
T
20
W
21
T
22
F
23
S
24
S
25
M
26
T
27
W
28
T
29
F
30
S
31
S
1
M
2
T
3
W
4
T
5
F
6
S
7
S
8
M
9
T
10
W
11
T
12
F
13
S
14
S
15
M
16
T
17
W
18
T
19
F
20
S
21
S
22
M
23
T
24
W
25
T
26
◆ Milestone
Commencement
13 Oct
Shoring installation complete
19 Oct
Pit works complete (pit wall)
11 Nov
Building foundation complete
18 Nov
Overall completion
24 Nov
A
Shoring system installation
—
6
13 Oct
19 Oct
6 d
B
Lean concrete
A · SS +6
2
20 Oct
21 Oct
C
Pit trench – reinforcement, formwork & concrete
A · FS
4
20 Oct
24 Oct
4 d
D
Pit slab / raft – reinforcement, formwork & concrete
C · FS
10
25 Oct
4 Nov
10 d
E
Pit wall – reinforcement, formwork & concrete
D · FS
6
5 Nov
11 Nov
6 d
F
Building foundation – excavation, compaction / testing, reinforcement & concrete
D · FS
12
5 Nov
18 Nov
12 d
G
Backfilling works for the building
F · FS
5
19 Nov
24 Nov
5 d
Status date · 21 Oct
Commencement
Tue 13 Oct 2026
Working day 1 / 37
Shoring installation complete
Mon 19 Oct 2026
Working day 6 / 37
Pit works complete (pit wall)
Wed 11 Nov 2026
Working day 26 / 37
Building foundation complete
Wed 18 Nov 2026
Working day 32 / 37
Overall completion
Tue 24 Nov 2026
Working day 37 / 37

## Slide 3
Shoring Activities & Planning Basis
Sequence of shoring works, key dates and conditions of the proposed programme
Shoring works sequence (Activity A)
13 October 2026 → 19 October 2026 · 6 working days
1
Excavation / digging for H-Beam
2
Installation of H-Beam
3
Concrete work for H-Beam
4
Bracing for shoring
5
Corrugated sheets installation / insertion
Key dates (automatic)
Commencement
Tue 13 Oct 2026
Shoring installation complete
Mon 19 Oct 2026
Pit works complete (pit wall)
Wed 11 Nov 2026
Building foundation complete
Wed 18 Nov 2026
Overall completion
Tue 24 Nov 2026
What-if scenario
If works start on 21 October 2026 (permit-ready date) → overall completion would be 2 December 2026 (+8 calendar days later than proposed).
Notes & conditions
Commencement of each activity is subject to issuance of the work permit and timely approval of Work Inspection Requests (WIRs) and Material Inspection Requests (MIRs). Any delay in permit issuance or WIR / MIR approval will shift the affected activity and all succeeding activities accordingly.
Working week is Saturday to Thursday. Fridays are non-working.
Lean concrete runs parallel to shoring (SS link) and is placed only in bays where shoring is installed.
Building foundation is linked to completion of the pit slab / raft (FS link) and runs parallel to the pit wall. Change its predecessor to E if it must follow the pit wall.
Source: Gulf Development Company for Contracting – Programme Rev 01 (12 Oct 2026), forwarded by SAR Construction Manager