## Dashboard
SAUDI ARABIA RAILWAY COMPANY ¦ ZULFI RAILWAY STATION – PROJECT COST & SCHEDULE DASHBOARD
WBS, Cost Breakdown Structure (CBS) and 26-month schedule generated from the Phased Bill of Quantities (16 March 2026).
Total Project Cost (excl. VAT) |  | VAT (15%) |  | Total Project Cost (incl. VAT) | Project Duration
99999000 |  | 14999850 |  | 114998850 | 26
Phase 1 Total (excl. VAT) |  |  |  | Phase 2 Total (excl. VAT)
65009000 |  |  |  | 34990000
WBS Group | Amount (SAR)
1.0 Preliminaries & General Requirements | 4900000
2.0 Design Works | 4889000
3.0 Main Building Works | 4550000
4.0 Ancillary Buildings | 8501000
5.0 External & Site Development Works | 12170000
6.0 Roads, Signalling & External Works | 34090000
7.0 Railway Track & Turnout Works | 30899000
Phase | Amount (SAR)
Phase 1 | 65009000
Phase 2 | 34990000

## WBS & CBS
ZULFI RAILWAY STATION ¦ WORK BREAKDOWN STRUCTURE (WBS) & COST BREAKDOWN STRUCTURE (CBS)
Amounts in SAR, excluding VAT. Rows in teal are Level-1 WBS groups; totals are SUM formulas of their child items. Month 1 is reserved for Access Permits (WBS 1.2); Concept Design Submission falls on Month 2, Approval on Month 3. Work Permit Approval (WBS 1.3, 14 days, Month 12) is successor to Detailed Design Approval and predecessor to construction commencement — every Installation & Construction activity is now driven by whichever is later: Work Permit Approval or its own Manufacture and Delivery to Site. Every construction item's procurement is broken into Vendor Prequalification (5%) → PO Issuance (15%) → Manufacture and Delivery to Site (80%), finish-to-start ahead of Installation & Construction using discipline-based cost weightage; items with a 4+ month lead are flagged Long-Lead (Yes). Phase 1 procurement may commence 15 days after Preliminary Design Approval (now Month 7); Phase 2 procurement may only commence after Detailed Design Approval (now Month 11). EPC Category classifies every detail row under Engineering / Procurement / Construction / General — see the EPC-level rollup below the totals.
WBS Code | Description | BOQ Ref | Phase | Unit | Qty | Rate (SAR) | Amount (SAR) | % of Total | Cumulative % | Long-Lead | Predecessor / Logical Link | EPC Category
1.0 | Preliminaries & General Requirements | [5 empty] | 4900000 | 4.9% | 4.9%
1.1 | Site establishment, mobilization, insurances/permits, HSE, project mgmt, testing labs, demobilization | 1.1 | Phase 1 | Lump Sum | Item |  | 4900000 | 4.9% | 4.9% | No | Project Start | General
1.2 | Access Permits – Request Submission & Approval (site access, right-of-entry, authority permits) | 1.1 | Phase 1 | Lump Sum | Item |  | 0 | 0% | 0% | No | Project Start | General
1.3 | Work Permit Approval (14 days) – authority sign-off enabling site construction works to commence | 1.1 | Phase 1 | Lump Sum | Item |  | 0 | 0% | 0% | No | FS: 2.6 Detailed Design - Approval | General
2.0 | Design Works | [5 empty] | 4889000 | 4.889% | 9.789%
2.1 | Concept Design - Submission | 2.1 | Phase 1 | Lump Sum | Item |  | 279371.4286 | 0.2794% | 0.2794% | No | FS: 1.2 Access Permits - Request Submission & Approval | Engineering
2.2 | Concept Design - Approval | 2.1 | Phase 1 | Lump Sum | Item |  | 419057.1429 | 0.4191% | 0.4191% | No | FS: 2.1 Concept Design - Submission | Engineering
2.3 | Preliminary Design - Submission | 2.1 | Phase 1 | Lump Sum | Item |  | 558742.8571 | 0.5587% | 0.5587% | No | FS: 2.2 Concept Design - Approval | Engineering
2.4 | Preliminary Design - Approval | 2.1 | Phase 1 | Lump Sum | Item |  | 838114.2857 | 0.8381% | 0.8381% | No | FS: 2.3 Preliminary Design - Submission | Engineering
2.5 | Detailed Design - Submission | 2.1 | Phase 1 | Lump Sum | Item |  | 1117485.7143 | 1.117% | 1.117% | No | FS: 2.4 Preliminary Design - Approval | Engineering
2.6 | Detailed Design - Approval | 2.1 | Phase 1 | Lump Sum | Item |  | 1676228.5714 | 1.676% | 1.676% | No | FS: 2.5 Detailed Design - Submission | Engineering
3.0 | Main Building Works | [5 empty] | 4550000 | 4.55% | 14.34%
3.1a1 | Main Building (GEA 1,100 m²) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 3.1 | Phase 1 | Lump Sum | Item |  | 22500 | 0.0225% | 0.0225% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
3.1a2 | Main Building (GEA 1,100 m²) – PO Issuance (Standard Lead, 15% of Procurement) | 3.1 | Phase 1 | Lump Sum | Item |  | 67500 | 0.0675% | 0.0675% | No | FS: 3.1a1 Main Building (GEA 1,100 m²) - Vendor Prequalification | Procurement
3.1a3 | Main Building (GEA 1,100 m²) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 3.1 | Phase 1 | Lump Sum | Item |  | 360000 | 0.36% | 0.36% | No | FS: 3.1a2 Main Building (GEA 1,100 m²) - PO Issuance | Procurement
3.1b | Main Building (GEA 1,100 m²) – Structure, Finishes, MEP, Fire & Life Safety, T&C | 3.1 | Phase 1 | Lump Sum | Item |  | 1800000 | 1.8% | 1.8% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.1a3 Main Building (GEA 1,100 m²) - Manufacture and Delivery to Site | Construction
3.2a1 | IT Equipment – Vendor Prequalification (Standard Lead, 5% of Procurement) | 3.2 | Phase 1 | Lump Sum | Item |  | 6000 | 0.006% | 0.006% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
3.2a2 | IT Equipment – PO Issuance (Standard Lead, 15% of Procurement) | 3.2 | Phase 1 | Lump Sum | Item |  | 18000 | 0.018% | 0.018% | No | FS: 3.2a1 IT Equipment - Vendor Prequalification | Procurement
3.2a3 | IT Equipment – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 3.2 | Phase 1 | Lump Sum | Item |  | 96000 | 0.096% | 0.096% | No | FS: 3.2a2 IT Equipment - PO Issuance | Procurement
3.2b | IT Equipment – Installation, Testing & Commissioning | 3.2 | Phase 1 | Lump Sum | Item |  | 280000 | 0.28% | 0.28% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.2a3 IT Equipment - Manufacture and Delivery to Site + 3.1b Main Building (substantially complete) | Construction
3.3a1 | Furniture, Fixtures & Equipment (FF&E) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 3.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 38000 | 0.038% | 0.038% | No | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | Procurement
3.3a2 | Furniture, Fixtures & Equipment (FF&E) – PO Issuance (Standard Lead, 15% of Procurement) | 3.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 114000 | 0.114% | 0.114% | No | FS: 3.3a1 Furniture, Fixtures & Equipment (FF&E) - Vendor Prequalification | Procurement
3.3a3 | Furniture, Fixtures & Equipment (FF&E) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 3.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 608000 | 0.608% | 0.608% | No | FS: 3.3a2 Furniture, Fixtures & Equipment (FF&E) - PO Issuance | Procurement
3.3b | Furniture, Fixtures & Equipment (FF&E) – Site Fixing, Installation & Handover | 3.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 1140000 | 1.14% | 1.14% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.3a3 Furniture, Fixtures & Equipment (FF&E) - Manufacture and Delivery to Site + 3.1b Main Building (structure & finishes) | Construction
4.0 | Ancillary Buildings | [5 empty] | 8501000 | 8.501% | 22.84%
4.1a1 | Substation & SEC Works – Vendor Prequalification (Long-Lead, 5% of Procurement) | 4.1 | Phase 1 | Lump Sum | Item |  | 55350 | 0.05535% | 0.05535% | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
4.1a2 | Substation & SEC Works – PO Issuance (Long-Lead, 15% of Procurement) | 4.1 | Phase 1 | Lump Sum | Item |  | 166050 | 0.1661% | 0.1661% | Yes | FS: 4.1a1 Substation & SEC Works - Vendor Prequalification | Procurement
4.1a3 | Substation & SEC Works – Manufacture and Delivery to Site (Long-Lead, 80% of Procurement) | 4.1 | Phase 1 | Lump Sum | Item |  | 885600 | 0.8856% | 0.8856% | Yes | FS: 4.1a2 Substation & SEC Works - PO Issuance | Procurement
4.1b | Substation & SEC Works – Civil, Installation, Testing & Energization | 4.1 | Phase 1 | Lump Sum | Item |  | 2583000 | 2.583% | 2.583% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.1a3 Substation & SEC Works - Manufacture and Delivery to Site | Construction
4.2a1 | Firefighting Building (GEA 518 m²) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 4.2 | Phase 1 | Lump Sum | Item |  | 14900 | 0.0149% | 0.0149% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
4.2a2 | Firefighting Building (GEA 518 m²) – PO Issuance (Standard Lead, 15% of Procurement) | 4.2 | Phase 1 | Lump Sum | Item |  | 44700 | 0.0447% | 0.0447% | No | FS: 4.2a1 Firefighting Building (GEA 518 m²) - Vendor Prequalification | Procurement
4.2a3 | Firefighting Building (GEA 518 m²) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 4.2 | Phase 1 | Lump Sum | Item |  | 238400 | 0.2384% | 0.2384% | No | FS: 4.2a2 Firefighting Building (GEA 518 m²) - PO Issuance | Procurement
4.2b | Firefighting Building (GEA 518 m²) – Civil Works, Fire Pump Room, Ring Main Integration | 4.2 | Phase 1 | Lump Sum | Item |  | 1192000 | 1.192% | 1.192% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.2a3 Firefighting Building (GEA 518 m²) - Manufacture and Delivery to Site | Construction
4.3a1 | Generator Room – Vendor Prequalification (Long-Lead, 5% of Procurement) | 4.3 (Ph.2) | Phase 2 | Lump Sum | Item |  | 14850 | 0.01485% | 0.01485% | Yes | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | Procurement
4.3a2 | Generator Room – PO Issuance (Long-Lead, 15% of Procurement) | 4.3 (Ph.2) | Phase 2 | Lump Sum | Item |  | 44550 | 0.04455% | 0.04455% | Yes | FS: 4.3a1 Generator Room - Vendor Prequalification | Procurement
4.3a3 | Generator Room – Manufacture and Delivery to Site (Long-Lead, 80% of Procurement) | 4.3 (Ph.2) | Phase 2 | Lump Sum | Item |  | 237600 | 0.2376% | 0.2376% | Yes | FS: 4.3a2 Generator Room - PO Issuance | Procurement
4.3b | Generator Room – Civil Works, Installation & Commissioning | 4.3 (Ph.2) | Phase 2 | Lump Sum | Item |  | 693000 | 0.693% | 0.693% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.3a3 Generator Room - Manufacture and Delivery to Site | Construction
4.4a1 | Underground Water Tank – Vendor Prequalification (Standard Lead, 5% of Procurement) | 4.4 | Phase 1 | Lump Sum | Item |  | 23310 | 0.02331% | 0.02331% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
4.4a2 | Underground Water Tank – PO Issuance (Standard Lead, 15% of Procurement) | 4.4 | Phase 1 | Lump Sum | Item |  | 69930 | 0.06993% | 0.06993% | No | FS: 4.4a1 Underground Water Tank - Vendor Prequalification | Procurement
4.4a3 | Underground Water Tank – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 4.4 | Phase 1 | Lump Sum | Item |  | 372960 | 0.373% | 0.373% | No | FS: 4.4a2 Underground Water Tank - PO Issuance | Procurement
4.4b | Underground Water Tank – Excavation, RC Tank, Waterproofing, Hydrostatic Testing | 4.4 | Phase 1 | Lump Sum | Item |  | 1864800 | 1.865% | 1.865% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.4a3 Underground Water Tank - Manufacture and Delivery to Site | Construction
5.0 | External & Site Development Works | [5 empty] | 12170000 | 12.17% | 35.01%
5.1a1 | Site Works & Underground Utilities (Plot 15,000 m²) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 5.1 | Phase 1 | Lump Sum | Item |  | 108800 | 0.1088% | 0.1088% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
5.1a2 | Site Works & Underground Utilities (Plot 15,000 m²) – PO Issuance (Standard Lead, 15% of Procurement) | 5.1 | Phase 1 | Lump Sum | Item |  | 326400 | 0.3264% | 0.3264% | No | FS: 5.1a1 Site Works & Underground Utilities (Plot 15,000 m²) - Vendor Prequalification | Procurement
5.1a3 | Site Works & Underground Utilities (Plot 15,000 m²) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 5.1 | Phase 1 | Lump Sum | Item |  | 1740800 | 1.741% | 1.741% | No | FS: 5.1a2 Site Works & Underground Utilities (Plot 15,000 m²) - PO Issuance | Procurement
5.1b | Site Works & Underground Utilities (Plot 15,000 m²) – Drainage, Water, FF Ring Main, Ducts – Installation | 5.1 | Phase 1 | Lump Sum | Item |  | 8704000 | 8.704% | 8.704% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.1a3 Site Works & Underground Utilities (Plot 15,000 m²) - Manufacture and Delivery to Site | Construction
5.2a1 | Car Parking Sheds (80 lots) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 5.2 | Phase 1 | Lump Sum | Item |  | 7900 | 0.0079% | 0.0079% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
5.2a2 | Car Parking Sheds (80 lots) – PO Issuance (Standard Lead, 15% of Procurement) | 5.2 | Phase 1 | Lump Sum | Item |  | 23700 | 0.0237% | 0.0237% | No | FS: 5.2a1 Car Parking Sheds (80 lots) - Vendor Prequalification | Procurement
5.2a3 | Car Parking Sheds (80 lots) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 5.2 | Phase 1 | Lump Sum | Item |  | 126400 | 0.1264% | 0.1264% | No | FS: 5.2a2 Car Parking Sheds (80 lots) - PO Issuance | Procurement
5.2b | Car Parking Sheds (80 lots) – Structural Erection & Finishes | 5.2 | Phase 1 | Lump Sum | Item |  | 632000 | 0.632% | 0.632% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.2a3 Car Parking Sheds (80 lots) - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (partial) | Construction
5.3a1 | Fence Works – Vendor Prequalification (Standard Lead, 5% of Procurement) | 5.3 | Phase 1 | Lump Sum | Item |  | 2000 | 0.002% | 0.002% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
5.3a2 | Fence Works – PO Issuance (Standard Lead, 15% of Procurement) | 5.3 | Phase 1 | Lump Sum | Item |  | 6000 | 0.006% | 0.006% | No | FS: 5.3a1 Fence Works - Vendor Prequalification | Procurement
5.3a3 | Fence Works – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 5.3 | Phase 1 | Lump Sum | Item |  | 32000 | 0.032% | 0.032% | No | FS: 5.3a2 Fence Works - PO Issuance | Procurement
5.3b | Fence Works – Chain Link Fence – Erection | 5.3 | Phase 1 | Lump Sum | Item |  | 160000 | 0.16% | 0.16% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.3a3 Fence Works - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (substantially complete) | Construction
5.4a1 | Automatic Gate System – Vendor Prequalification (Standard Lead, 5% of Procurement) | 5.4 | Phase 1 | Lump Sum | Item |  | 4500 | 0.0045% | 0.0045% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
5.4a2 | Automatic Gate System – PO Issuance (Standard Lead, 15% of Procurement) | 5.4 | Phase 1 | Lump Sum | Item |  | 13500 | 0.0135% | 0.0135% | No | FS: 5.4a1 Automatic Gate System - Vendor Prequalification | Procurement
5.4a3 | Automatic Gate System – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 5.4 | Phase 1 | Lump Sum | Item |  | 72000 | 0.072% | 0.072% | No | FS: 5.4a2 Automatic Gate System - PO Issuance | Procurement
5.4b | Automatic Gate System – Boom Barrier Installation & Commissioning | 5.4 | Phase 1 | Lump Sum | Item |  | 210000 | 0.21% | 0.21% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.4a3 Automatic Gate System - Manufacture and Delivery to Site + 5.3b Fence Works (substantially complete) | Construction
6.0 | Roads, Signalling & External Works | [5 empty] | 34090000 | 34.09% | 69.1%
6.1a1 | Access Road (1,700 m, dual carriageway) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 6.1 (Ph.2) | Phase 2 | Lump Sum | Item |  | 102000 | 0.102% | 0.102% | No | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | Procurement
6.1a2 | Access Road (1,700 m, dual carriageway) – PO Issuance (Standard Lead, 15% of Procurement) | 6.1 (Ph.2) | Phase 2 | Lump Sum | Item |  | 306000 | 0.306% | 0.306% | No | FS: 6.1a1 Access Road (1,700 m, dual carriageway) - Vendor Prequalification | Procurement
6.1a3 | Access Road (1,700 m, dual carriageway) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 6.1 (Ph.2) | Phase 2 | Lump Sum | Item |  | 1632000 | 1.632% | 1.632% | No | FS: 6.1a2 Access Road (1,700 m, dual carriageway) - PO Issuance | Procurement
6.1b | Access Road (1,700 m, dual carriageway) – Pavement, Lighting, Drainage, Signage – Installation | 6.1 (Ph.2) | Phase 2 | Lump Sum | Item |  | 8160000 | 8.16% | 8.16% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.1a3 Access Road (1,700 m, dual carriageway) - Manufacture and Delivery to Site | Construction
6.2a1 | Signalling & Telecommunication – Vendor Prequalification (Long-Lead, 5% of Procurement) | 6.2 | Phase 1 | Lump Sum | Item |  | 335250 | 0.3353% | 0.3353% | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
6.2a2 | Signalling & Telecommunication – PO Issuance (Long-Lead, 15% of Procurement) | 6.2 | Phase 1 | Lump Sum | Item |  | 1005750 | 1.006% | 1.006% | Yes | FS: 6.2a1 Signalling & Telecommunication - Vendor Prequalification | Procurement
6.2a3 | Signalling & Telecommunication – Manufacture and Delivery to Site (incl. FAT) (Long-Lead, 80% of Procurement) | 6.2 | Phase 1 | Lump Sum | Item |  | 5364000 | 5.364% | 5.364% | Yes | FS: 6.2a2 Signalling & Telecommunication - PO Issuance | Procurement
6.2b | Signalling & Telecommunication – Installation, Integration, Testing & Commissioning | 6.2 | Phase 1 | Lump Sum | Item |  | 8195000 | 8.195% | 8.195% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.2a3 Signalling & Telecommunication - Manufacture and Delivery to Site | Construction
6.3a1 | External Works (above ground) – Vendor Prequalification (Standard Lead, 5% of Procurement) | 6.3 | Phase 1 | Lump Sum | Item |  | 89900 | 0.0899% | 0.0899% | No | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
6.3a2 | External Works (above ground) – PO Issuance (Standard Lead, 15% of Procurement) | 6.3 | Phase 1 | Lump Sum | Item |  | 269700 | 0.2697% | 0.2697% | No | FS: 6.3a1 External Works (above ground) - Vendor Prequalification | Procurement
6.3a3 | External Works (above ground) – Manufacture and Delivery to Site (Standard Lead, 80% of Procurement) | 6.3 | Phase 1 | Lump Sum | Item |  | 1438400 | 1.438% | 1.438% | No | FS: 6.3a2 External Works (above ground) - PO Issuance | Procurement
6.3b | External Works (above ground) – Roads, Footpaths, Landscaping, Guard Houses | 6.3 | Phase 1 | Lump Sum | Item |  | 7192000 | 7.192% | 7.192% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.3a3 External Works (above ground) - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (partial) | Construction
7.0 | Railway Track & Turnout Works | [5 empty] | 30899000 | 30.9% | 100%
7.2a1 | Railway Track Works (Loop Line, 2,500 m) – Vendor Prequalification (Long-Lead, 5% of Procurement) | 7.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 492750 | 0.4928% | 0.4928% | Yes | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | Procurement
7.2a2 | Railway Track Works (Loop Line, 2,500 m) – PO Issuance (Long-Lead, 15% of Procurement) | 7.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 1478250 | 1.478% | 1.478% | Yes | FS: 7.2a1 Railway Track Works (Loop Line, 2,500 m) - Vendor Prequalification | Procurement
7.2a3 | Railway Track Works (Loop Line, 2,500 m) – Manufacture and Delivery to Site (incl. FAT) (Long-Lead, 80% of Procurement) | 7.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 7884000 | 7.884% | 7.884% | Yes | FS: 7.2a2 Railway Track Works (Loop Line, 2,500 m) - PO Issuance | Procurement
7.2b | Railway Track Works (Loop Line, 2,500 m) – Formation, Laying, Alignment, Testing & Commissioning | 7.2 (Ph.2) | Phase 2 | Lump Sum | Item |  | 12045000 | 12.05% | 12.05% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 7.2a3 Railway Track Works (Loop Line, 2,500 m) - Manufacture and Delivery to Site | Construction
7.3a1 | Railway Turnout Works – Vendor Prequalification (Long-Lead, 5% of Procurement) | 7.3 | Phase 1 | Lump Sum | Item |  | 202477.5 | 0.2025% | 0.2025% | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | Procurement
7.3a2 | Railway Turnout Works – PO Issuance (Long-Lead, 15% of Procurement) | 7.3 | Phase 1 | Lump Sum | Item |  | 607432.5 | 0.6074% | 0.6074% | Yes | FS: 7.3a1 Railway Turnout Works - Vendor Prequalification | Procurement
7.3a3 | Railway Turnout Works – Manufacture and Delivery to Site (incl. FAT) (Long-Lead, 80% of Procurement) | 7.3 | Phase 1 | Lump Sum | Item |  | 3239640 | 3.24% | 3.24% | Yes | FS: 7.3a2 Railway Turnout Works - PO Issuance | Procurement
7.3b | Railway Turnout Works – Installation, Alignment, Tie-in, Testing & Commissioning | 7.3 | Phase 1 | Lump Sum | Item |  | 4949450 | 4.949% | 4.949% | No | Driven by later of: FS 1.3 Work Permit Approval / FS 7.3a3 Railway Turnout Works - Manufacture and Delivery to Site + 7.2b Railway Track Works (concurrent — foundation/bed prep precedes Track, tie-in concurrent with Track's final stages) | Construction
| TOTAL PROJECT COST (excl. VAT) | [5 empty] | 99999000
| VAT (15%) | [5 empty] | 14999850
| TOTAL PROJECT COST (incl. VAT) | [5 empty] | 114998850
EPC LEVEL-0 WBS SUMMARY
EPC Code | Category | Amount (SAR) | % of Total
G.0 | General / Preliminaries | 4900000 | 4.9%
E.0 | Engineering (Design Works) | 4889000 | 4.889%
P.0 | Procurement of Materials | 30409750 | 30.41%
C.0 | Installation & Construction | 59800250 | 59.8%
| TOTAL PROJECT COST (excl. VAT) | 99999000

## 26-Month Schedule
ZULFI RAILWAY STATION ¦ 26-MONTH PROJECT SCHEDULE (GANTT) & COST-LOADED CASH FLOW
Preliminaries & General Requirements are cost-loaded evenly across the full Months 1–26. Month 1 is reserved solely for Access Permits (WBS 1.2, Request Submission & Approval). Design Works span Months 2–11 (11 months, extended from 9): Concept Design Submission on Month 2, Approval on Month 3 (client-specified, 2 full months instead of both sub-activities sharing Month 1) → Preliminary (30%, 3mo, M4-6) → Detailed (60%, 5mo, M7-11), finish-to-start, normalized to 100% (raw weights summed to 105%); each stage's Submission (40%) → Approval (60%) sub-activities are also finish-to-start. Work Permit Approval (WBS 1.3, 14 days → 1-month row, Month 12) is successor to Detailed Design Approval (WBS 2.6) and predecessor to construction commencement: every Installation & Construction activity is now driven by whichever gate is LATER — Work Permit Approval (Month 13 earliest) or its own Manufacture and Delivery to Site completion (whichever is binding is shown in the Predecessor column). EVERY procurement/construction item (codes ending 'a1'/'a2'/'a3'/'b') is split into Vendor Prequalification (5%) → PO Issuance (15%) → Manufacture and Delivery to Site (80%), sequential finish-to-start. Phase 1 procurement may commence 15 days after Preliminary Design Approval (WBS 2.4, now ends Month 6), i.e. Month 7 at the earliest. Phase 2 procurement (Furniture, Generator Room, Access Road, Railway Track) may only commence after Detailed Design Approval (Month 11) — a stricter gate than Phase 1. The materials/construction split follows discipline-based logical weightage, with Construction always the higher share: Civil & Site Works 20%/80%, MEP & Mechanical Equipment 30%/70%, Specialised Rail & Signalling Systems 45%/55%, Furniture/Fit-out 40%/60%. Items with a 4+ month lead are flagged Long-Lead. For Signalling & Telecom, Railway Track and Railway Turnout, Manufacture and Delivery to Site is set to a minimum 8-month duration. CRITICAL NOTE: the Work Permit Approval gate (Month 13) is now the binding constraint for Main Building, Substation, Firefighting Building, Water Tank and Site Works & Utilities — all pushed to start Month 13, later than their own material-delivery readiness. This ripples through every activity that cascades off them, and combined with the earlier design-phase extension, several Installation durations are now compressed to still finish by Month 26: IT Equipment 4mo, Fence Works 4mo, External Works 7mo, Automatic Gate and Furniture (FF&E) only 2mo each. Railway Track remains compressed to 6 months (Phase 2 gate, unaffected by the 15-day change). This is a materially tight tail end of the programme — extending total project duration beyond 26 months, or streamlining the front-end approval sequence (Access Permits → Concept Design → Work Permit), would meaningfully relieve it. Installation & Construction activities are cost-loaded with a triangular ramp-up / peak / ramp-down weightage across their own duration. The 25% Year-1 cash-flow cap remains removed (Year 1/Year 2 totals below are informational only). Shaded cells mark active months; adjust Start/End Month cells to re-sequence — monthly cash flow updates automatically.
WBS Code | Description | Phase | EPC | Amount (SAR) | Start Month | End Month | Duration (Mo) | Long-Lead | Predecessor / Logical Link | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | Check | Weight helper grid (hidden) — triangular ramp-up/peak/ramp-down per activity
1.1 | Preliminaries & General Requirements | Phase 1 | GEN | 4900000 | 1 | 26 | 26 | No | Project Start | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 188461.5385 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 182
1.2 | Access Permits – Request Submission & Approval | Phase 1 | GEN | 0 | 1 | 1 | 1 | No | Project Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
1.3 | Work Permit Approval | Phase 1 | GEN | 0 | 12 | 12 | 1 | No | FS: 2.6 Detailed Design - Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2.1 | Concept Design - Submission | Phase 1 | ENG | 279371.4286 | 2 | 2 | 1 | No | FS: 1.2 Access Permits - Request Submission & Approval | 0 | 279371.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2.2 | Concept Design - Approval | Phase 1 | ENG | 419057.1429 | 3 | 3 | 1 | No | FS: 2.1 Concept Design - Submission | 0 | 0 | 419057.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2.3 | Preliminary Design - Submission | Phase 1 | ENG | 558742.8571 | 4 | 4 | 1 | No | FS: 2.2 Concept Design - Approval | 0 | 0 | 0 | 558742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2.4 | Preliminary Design - Approval | Phase 1 | ENG | 838114.2857 | 5 | 6 | 2 | No | FS: 2.3 Preliminary Design - Submission | 0 | 0 | 0 | 0 | 419057.1429 | 419057.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2.5 | Detailed Design - Submission | Phase 1 | ENG | 1117485.7143 | 7 | 8 | 2 | No | FS: 2.4 Preliminary Design - Approval | 0 | 0 | 0 | 0 | 0 | 0 | 558742.8571 | 558742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2.6 | Detailed Design - Approval | Phase 1 | ENG | 1676228.5714 | 9 | 11 | 3 | No | FS: 2.5 Detailed Design - Submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558742.8571 | 558742.8571 | 558742.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3.1a1 | Main Building – Vendor Prequalification | Phase 1 | PROC | 22500 | 11 | 11 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3.1a2 | Main Building – PO Issuance | Phase 1 | PROC | 67500 | 11 | 11 | 1 | No | FS: 3.1a1 Main Building (GEA 1,100 m²) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3.1a3 | Main Building – Manufacture and Delivery to Site | Phase 1 | PROC | 360000 | 12 | 12 | 1 | No | FS: 3.1a2 Main Building (GEA 1,100 m²) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3.1b | Main Building – Installation & Construction | Phase 1 | CONS | 1800000 | 13 | 24 | 12 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.1a3 Main Building (GEA 1,100 m²) - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42857.1429 | 85714.2857 | 128571.4286 | 171428.5714 | 214285.7143 | 257142.8571 | 257142.8571 | 214285.7143 | 171428.5714 | 128571.4286 | 85714.2857 | 42857.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 42
3.2a1 | IT Equipment – Vendor Prequalification | Phase 1 | PROC | 6000 | 21 | 21 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
3.2a2 | IT Equipment – PO Issuance | Phase 1 | PROC | 18000 | 21 | 21 | 1 | No | FS: 3.2a1 IT Equipment - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
3.2a3 | IT Equipment – Manufacture and Delivery to Site | Phase 1 | PROC | 96000 | 22 | 22 | 1 | No | FS: 3.2a2 IT Equipment - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
3.2b | IT Equipment – Installation & Construction | Phase 1 | CONS | 280000 | 23 | 26 | 4 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.2a3 IT Equipment - Manufacture and Delivery to Site + 3.1b Main Building (substantially complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46666.6667 | 93333.3333 | 93333.3333 | 46666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 6
3.3a1 | Furniture (FF&E) – Vendor Prequalification | Phase 2 | PROC | 38000 | 22 | 22 | 1 | No | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
3.3a2 | Furniture (FF&E) – PO Issuance | Phase 2 | PROC | 114000 | 23 | 23 | 1 | No | FS: 3.3a1 Furniture, Fixtures & Equipment (FF&E) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
3.3a3 | Furniture (FF&E) – Manufacture and Delivery to Site | Phase 2 | PROC | 608000 | 24 | 24 | 1 | No | FS: 3.3a2 Furniture, Fixtures & Equipment (FF&E) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
3.3b | Furniture (FF&E) – Installation & Construction | Phase 2 | CONS | 1140000 | 25 | 26 | 2 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 3.3a3 Furniture, Fixtures & Equipment (FF&E) - Manufacture and Delivery to Site + 3.1b Main Building (structure & finishes) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
4.1a1 | Substation & SEC – Vendor Prequalification | Phase 1 | PROC | 55350 | 8 | 8 | 1 | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.1a2 | Substation & SEC – PO Issuance | Phase 1 | PROC | 166050 | 9 | 9 | 1 | Yes | FS: 4.1a1 Substation & SEC Works - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.1a3 | Substation & SEC – Manufacture and Delivery to Site | Phase 1 | PROC | 885600 | 10 | 12 | 3 | Yes | FS: 4.1a2 Substation & SEC Works - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295200 | 295200 | 295200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4.1b | Substation & SEC – Installation & Construction | Phase 1 | CONS | 2583000 | 13 | 22 | 10 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.1a3 Substation & SEC Works - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86100 | 172200 | 258300 | 344400 | 430500 | 430500 | 344400 | 258300 | 172200 | 86100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 30
4.2a1 | Firefighting Bldg – Vendor Prequalification | Phase 1 | PROC | 14900 | 11 | 11 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.2a2 | Firefighting Bldg – PO Issuance | Phase 1 | PROC | 44700 | 11 | 11 | 1 | No | FS: 4.2a1 Firefighting Building (GEA 518 m²) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.2a3 | Firefighting Bldg – Manufacture and Delivery to Site | Phase 1 | PROC | 238400 | 12 | 12 | 1 | No | FS: 4.2a2 Firefighting Building (GEA 518 m²) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.2b | Firefighting Bldg – Installation & Construction | Phase 1 | CONS | 1192000 | 13 | 21 | 9 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.2a3 Firefighting Building (GEA 518 m²) - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47680 | 95360 | 143040 | 190720 | 238400 | 190720 | 143040 | 95360 | 47680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 25
4.3a1 | Generator Room – Vendor Prequalification | Phase 2 | PROC | 14850 | 11 | 11 | 1 | Yes | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.3a2 | Generator Room – PO Issuance | Phase 2 | PROC | 44550 | 12 | 12 | 1 | Yes | FS: 4.3a1 Generator Room - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.3a3 | Generator Room – Manufacture and Delivery to Site | Phase 2 | PROC | 237600 | 13 | 14 | 2 | Yes | FS: 4.3a2 Generator Room - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118800 | 118800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
4.3b | Generator Room – Installation & Construction | Phase 2 | CONS | 693000 | 15 | 21 | 7 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.3a3 Generator Room - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43312.5 | 86625 | 129937.5 | 173250 | 129937.5 | 86625 | 43312.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 16
4.4a1 | Water Tank – Vendor Prequalification | Phase 1 | PROC | 23310 | 12 | 12 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.4a2 | Water Tank – PO Issuance | Phase 1 | PROC | 69930 | 12 | 12 | 1 | No | FS: 4.4a1 Underground Water Tank - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.4a3 | Water Tank – Manufacture and Delivery to Site | Phase 1 | PROC | 372960 | 12 | 12 | 1 | No | FS: 4.4a2 Underground Water Tank - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
4.4b | Water Tank – Installation & Construction | Phase 1 | CONS | 1864800 | 13 | 18 | 6 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 4.4a3 Underground Water Tank - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155400 | 310800 | 466200 | 466200 | 310800 | 155400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
5.1a1 | Site Works & Utilities – Vendor Prequalification | Phase 1 | PROC | 108800 | 11 | 11 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.1a2 | Site Works & Utilities – PO Issuance | Phase 1 | PROC | 326400 | 11 | 11 | 1 | No | FS: 5.1a1 Site Works & Underground Utilities (Plot 15,000 m²) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.1a3 | Site Works & Utilities – Manufacture and Delivery to Site | Phase 1 | PROC | 1740800 | 12 | 12 | 1 | No | FS: 5.1a2 Site Works & Underground Utilities (Plot 15,000 m²) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.1b | Site Works & Utilities – Installation & Construction | Phase 1 | CONS | 8704000 | 13 | 22 | 10 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.1a3 Site Works & Underground Utilities (Plot 15,000 m²) - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290133.3333 | 580266.6667 | 870400 | 1160533.3333 | 1450666.6667 | 1450666.6667 | 1160533.3333 | 870400 | 580266.6667 | 290133.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 30
5.2a1 | Car Parking Sheds – Vendor Prequalification | Phase 1 | PROC | 7900 | 18 | 18 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.2a2 | Car Parking Sheds – PO Issuance | Phase 1 | PROC | 23700 | 18 | 18 | 1 | No | FS: 5.2a1 Car Parking Sheds (80 lots) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.2a3 | Car Parking Sheds – Manufacture and Delivery to Site | Phase 1 | PROC | 126400 | 19 | 19 | 1 | No | FS: 5.2a2 Car Parking Sheds (80 lots) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5.2b | Car Parking Sheds – Installation & Construction | Phase 1 | CONS | 632000 | 20 | 25 | 6 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.2a3 Car Parking Sheds (80 lots) - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (partial) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52666.6667 | 105333.3333 | 158000 | 158000 | 105333.3333 | 52666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 1 | 0 | 12
5.3a1 | Fence Works – Vendor Prequalification | Phase 1 | PROC | 2000 | 22 | 22 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
5.3a2 | Fence Works – PO Issuance | Phase 1 | PROC | 6000 | 22 | 22 | 1 | No | FS: 5.3a1 Fence Works - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
5.3a3 | Fence Works – Manufacture and Delivery to Site | Phase 1 | PROC | 32000 | 22 | 22 | 1 | No | FS: 5.3a2 Fence Works - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
5.3b | Fence Works – Installation & Construction | Phase 1 | CONS | 160000 | 23 | 26 | 4 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.3a3 Fence Works - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (substantially complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26666.6667 | 53333.3333 | 53333.3333 | 26666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 6
5.4a1 | Automatic Gate – Vendor Prequalification | Phase 1 | PROC | 4500 | 23 | 23 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
5.4a2 | Automatic Gate – PO Issuance | Phase 1 | PROC | 13500 | 23 | 23 | 1 | No | FS: 5.4a1 Automatic Gate System - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
5.4a3 | Automatic Gate – Manufacture and Delivery to Site | Phase 1 | PROC | 72000 | 24 | 24 | 1 | No | FS: 5.4a2 Automatic Gate System - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
5.4b | Automatic Gate – Installation & Construction | Phase 1 | CONS | 210000 | 25 | 26 | 2 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 5.4a3 Automatic Gate System - Manufacture and Delivery to Site + 5.3b Fence Works (substantially complete) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
6.1a1 | Access Road – Vendor Prequalification | Phase 2 | PROC | 102000 | 11 | 11 | 1 | No | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.1a2 | Access Road – PO Issuance | Phase 2 | PROC | 306000 | 11 | 11 | 1 | No | FS: 6.1a1 Access Road (1,700 m, dual carriageway) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.1a3 | Access Road – Manufacture and Delivery to Site | Phase 2 | PROC | 1632000 | 12 | 12 | 1 | No | FS: 6.1a2 Access Road (1,700 m, dual carriageway) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.1b | Access Road – Installation & Construction | Phase 2 | CONS | 8160000 | 13 | 25 | 13 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.1a3 Access Road (1,700 m, dual carriageway) - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166530.6122 | 333061.2245 | 499591.8367 | 666122.449 | 832653.0612 | 999183.6735 | 1165714.2857 | 999183.6735 | 832653.0612 | 666122.449 | 499591.8367 | 333061.2245 | 166530.6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 49
6.2a1 | Signalling & Telecom – Vendor Prequalification | Phase 1 | PROC | 335250 | 7 | 7 | 1 | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 335250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.2a2 | Signalling & Telecom – PO Issuance | Phase 1 | PROC | 1005750 | 8 | 8 | 1 | Yes | FS: 6.2a1 Signalling & Telecommunication - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.2a3 | Signalling & Telecom – Manufacture and Delivery to Site | Phase 1 | PROC | 5364000 | 9 | 16 | 8 | Yes | FS: 6.2a2 Signalling & Telecommunication - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670500 | 670500 | 670500 | 670500 | 670500 | 670500 | 670500 | 670500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
6.2b | Signalling & Telecom – Installation & Construction | Phase 1 | CONS | 8195000 | 17 | 26 | 10 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.2a3 Signalling & Telecommunication - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273166.6667 | 546333.3333 | 819500 | 1092666.6667 | 1365833.3333 | 1365833.3333 | 1092666.6667 | 819500 | 546333.3333 | 273166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 5 | 4 | 3 | 2 | 1 | 30
6.3a1 | External Works – Vendor Prequalification | Phase 1 | PROC | 89900 | 18 | 18 | 1 | No | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.3a2 | External Works – PO Issuance | Phase 1 | PROC | 269700 | 18 | 18 | 1 | No | FS: 6.3a1 External Works (above ground) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.3a3 | External Works – Manufacture and Delivery to Site | Phase 1 | PROC | 1438400 | 19 | 19 | 1 | No | FS: 6.3a2 External Works (above ground) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.3b | External Works – Installation & Construction | Phase 1 | CONS | 7192000 | 20 | 26 | 7 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 6.3a3 External Works (above ground) - Manufacture and Delivery to Site + 5.1b Site Works & Underground Utilities (partial) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449500 | 899000 | 1348500 | 1798000 | 1348500 | 899000 | 449500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 3 | 2 | 1 | 16
7.2a1 | Railway Track – Vendor Prequalification | Phase 2 | PROC | 492750 | 11 | 11 | 1 | Yes | FS: 2.6 Detailed Design - Approval (Phase 2 procurement gate) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
7.2a2 | Railway Track – PO Issuance | Phase 2 | PROC | 1478250 | 12 | 12 | 1 | Yes | FS: 7.2a1 Railway Track Works (Loop Line, 2,500 m) - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1478250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
7.2a3 | Railway Track – Manufacture and Delivery to Site | Phase 2 | PROC | 7884000 | 13 | 20 | 8 | Yes | FS: 7.2a2 Railway Track Works (Loop Line, 2,500 m) - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985500 | 985500 | 985500 | 985500 | 985500 | 985500 | 985500 | 985500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 20
7.2b | Railway Track – Installation & Construction | Phase 2 | CONS | 12045000 | 21 | 26 | 6 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 7.2a3 Railway Track Works (Loop Line, 2,500 m) - Manufacture and Delivery to Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1003750 | 2007500 | 3011250 | 3011250 | 2007500 | 1003750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 2 | 1 | 12
7.3a1 | Railway Turnout – Vendor Prequalification | Phase 1 | PROC | 202477.5 | 7 | 7 | 1 | Yes | FS: 2.4 Preliminary Design - Approval + 15 days | 0 | 0 | 0 | 0 | 0 | 0 | 202477.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
7.3a2 | Railway Turnout – PO Issuance | Phase 1 | PROC | 607432.5 | 8 | 8 | 1 | Yes | FS: 7.3a1 Railway Turnout Works - Vendor Prequalification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607432.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
7.3a3 | Railway Turnout – Manufacture and Delivery to Site | Phase 1 | PROC | 3239640 | 9 | 16 | 8 | Yes | FS: 7.3a2 Railway Turnout Works - PO Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404955 | 404955 | 404955 | 404955 | 404955 | 404955 | 404955 | 404955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
7.3b | Railway Turnout – Installation & Construction | Phase 1 | CONS | 4949450 | 17 | 26 | 10 | No | Driven by later of: FS 1.3 Work Permit Approval / FS 7.3a3 Railway Turnout Works - Manufacture and Delivery to Site + 7.2b Railway Track Works (concurrent — foundation/bed prep precedes Track, tie-in concurrent with Track's final stages) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164981.6667 | 329963.3333 | 494945 | 659926.6667 | 824908.3333 | 824908.3333 | 659926.6667 | 494945 | 329963.3333 | 164981.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 5 | 4 | 3 | 2 | 1 | 30
| (month index – helper row) | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | WtSum
| TOTAL MONTHLY SPEND (SAR) |  |  | 99999000 | [5 empty] | 188461.5385 | 467832.967 | 607518.6813 | 747204.3956 | 607518.6813 | 607518.6813 | 1284931.8956 | 2415736.8956 | 1988709.3956 | 2117859.3956 | 3618259.3956 | 7519316.5385 | 3156917.6269 | 3945618.7153 | 4658832.3038 | 5335445.8922 | 5219352.814 | 6098321.4024 | 7253974.5147 | 5952875.9262 | 6258827.3378 | 7238130.416 | 7698944.3276 | 7170574.9058 | 5012122.1507 | 2828193.2051
| CUMULATIVE SPEND (SAR) | [8 empty] | 188461.5385 | 656294.5055 | 1263813.1868 | 2011017.5824 | 2618536.2637 | 3226054.9451 | 4510986.8407 | 6926723.7363 | 8915433.1319 | 11033292.5275 | 14651551.9231 | 22170868.4615 | 25327786.0884 | 29273404.8038 | 33932237.1075 | 39267682.9997 | 44487035.8137 | 50585357.2161 | 57839331.7308 | 63792207.657 | 70051034.9948 | 77289165.4108 | 84988109.7384 | 92158684.6442 | 97170806.7949 | 99999000
| CUMULATIVE % COMPLETE (COST) | [8 empty] | 0.1885% | 0.6563% | 1.264% | 2.011% | 2.619% | 3.226% | 4.511% | 6.927% | 8.916% | 11.03% | 14.65% | 22.17% | 25.33% | 29.27% | 33.93% | 39.27% | 44.49% | 50.59% | 57.84% | 63.79% | 70.05% | 77.29% | 84.99% | 92.16% | 97.17% | 100%
| YEAR 1 (M1-M12) SPEND (SAR) |  |  | 22170868.4615
| YEAR 1 % OF CONTRACT VALUE |  |  | 22.17%
| YEAR 2 (M13-M26) SPEND (SAR) |  |  | 77828131.5385

## Assumptions & Weightages
ZULFI RAILWAY STATION ¦ ASSUMPTIONS & WEIGHTAGES REFERENCE
Consolidated reference for every weighting rule and schedule gate used to build the WBS, CBS and 26-Month Schedule. Change a rule here, then re-generate the workbook — these figures drive every formula elsewhere.
1. Discipline-Based Materials / Construction Cost Weightage
Discipline | Materials % | Construction % | Applies To (WBS Items)
Civil & Site Works | 20% | 80% | Main Building, Firefighting Building, Water Tank, Site Works & Utilities, Car Parking Sheds, Fence Works, Access Road, External Works
MEP & Mechanical Equipment | 30% | 70% | Substation & SEC Works, Generator Room, IT Equipment, Automatic Gate System
Specialised Rail & Signalling Systems | 45% | 55% | Signalling & Telecom, Railway Track Works, Railway Turnout Works
Furniture / Fit-out | 40% | 60% | Furniture, Fixtures & Equipment (FF&E)
Rule: Construction is always the higher weightage of the two (materials-heavy items are still labour/installation dominant).
2. Procurement Stage Weightage (applies within each item's Procurement cost share)
Procurement Stage | Weight | Notes
Vendor Prequalification | 5%
PO Issuance | 15%
Manufacture and Delivery to Site | 80% | Minimum 8 months for Signalling & Telecom, Railway Track and Railway Turnout (includes manufacturing & FAT) — overrides normal duration rounding
Sequence: Vendor Prequalification → PO Issuance → Manufacture and Delivery to Site, strictly finish-to-start.
3. Design Stage Weightage (of Design Works total, SAR 4,889,000)
Design Stage | Raw Weight | Normalized Weight | Duration
Concept Design | 15% | 14.29% | 1 mo (M2)
Preliminary Design | 30% | 28.57% | 3 mo (M4-6)
Detailed Design | 60% | 57.14% | 5 mo (M7-11)
Raw weights sum to 105%, not 100% — normalized proportionally so the design total still equals SAR 4,889,000 exactly.
4. Design Sub-Activity Weightage (within each design stage)
Sub-Activity | Weight
Submission | 40%
Approval | 60%
5. Schedule Gates & Other Key Assumptions
Rule | Value
Access Permits (Request Submission & Approval) | Month 1 only
Concept Design Submission / Approval | Month 2 / Month 3
Work Permit Approval duration | 14 days (1-month schedule row)
Work Permit Approval predecessor | FS: Detailed Design Approval (WBS 2.6)
Construction commencement driven by | Later of: Work Permit Approval OR own Manufacture and Delivery to Site
Phase 1 procurement lag after Preliminary Design Approval | 15 days
Phase 2 procurement gate | After Detailed Design Approval (stricter than Phase 1)
Long-Lead threshold | 4+ months lead time
Total project duration | 26 months (fixed)