## Report
[10 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
EWR CULVERTS REPLACEMENT PHASE 2
POSSESSION PROGRESS REPORT - PLANNED vs ACTUAL
Culvert Replacement – Shutdown 03
REPORT GENERATED
POSSESSION WINDOW
ELAPSED / REMAINING
SUMMARY - ALL LOCATIONS
Location |  | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Actual % | Buffer to Hand-back |  | 0: PROGRESS 0 - 100% coloured bar = actual % black line = DATA DATE
C263 – KM 209+025 (1 cell)
C265 – KM 210+525 (3 cells)
C267 – KM 212+400 (3 cells)
C288 – KM 337+391 (3 cells)
C289 – KM 338+491 (3 cells)
ALL LOCATIONS | bar: 0
SITE LAYOUT - SCHEMATIC OVERVIEW
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C263 - KM 209+025 - 1 CELL - TSO OTMP / Station 29
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back | bar: 0; 24
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C265 - KM 210+525 - 3 CELLS - TSO OTMP / Station 29
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back | bar: 0; 24
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C267 - KM 212+400 - 3 CELLS - TSO OTMP / Station 29
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back | bar: 0; 24
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C288 - KM 337+391 - 3 CELLS - SABATCO OTMP / Station 35
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back | bar: 0; 24
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast
EWR CULVERTS REPLACEMENT PHASE 2 - CULVERT C289 - KM 338+491 - 3 CELLS - SABATCO OTMP / Station 35
No | Activity | Status | Planned Finish | Forecast Finish | Time Variance | Plan % | Act. % | Buffer to Hand-back | bar: 0; 24
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
[9 empty] | P | [48 empty] | 1 | -999 | -999
A
| Planned (baseline) |  | Black line = report cut-off |  |  | Time Variance = Forecast vs Planned Finish |  |  |  | 5: Done on time; 14: Done late; 23: In progress; 32: Behind; 41: Forecast

## Site Layouts
EWR CULVERTS REPLACEMENT PHASE 2 – SHUTDOWN 03 – SITE LAYOUTS
CULVERTS C263 · C265 · C267 – KM 209+025 / 210+525 / 212+400
TSO OTMP stabled at Station 29 (KM 223) before the shutdown, then run out to Main Line 1 and Main Line 3. Hofuf lies to the west, Riyadh to the east.
EWR CULVERTS REPLACEMENT PHASE 2 – SHUTDOWN 03 – SITE LAYOUTS
CULVERTS C288 · C289 – KM 337+391 / 338+491
SABATCO OTMP works Line 1 at both culverts (Phase 1), then transfers to Line 3 via Station 35 (Phase 2). Station 33 lies at KM 309.
Diagrams as supplied with the Shutdown 03 pack. They show OTMP movement phases for each culvert group, not individual culvert cross-sections.

## Data Input
SAR - POSSESSION PROGRESS REPORT ¦ DATA INPUT AND SETTINGS
Everything below drives the report. Yellow cells are yours to edit - every other cell is locked and calculated. | [15 empty] | FS
SS
PROJECT NAME |  | EWR CULVERTS REPLACEMENT PHASE 2 | [5 empty] | REPORT TITLE |  | POSSESSION PROGRESS REPORT - PLANNED vs ACTUAL | [5 empty] | FF
SUBTITLE |  | Culvert Replacement – Shutdown 03 |  |  |  | PREPARED BY |  | SAR IPMC – Planning |  | REPORT CUT-OFF | [5 empty] | SF
POSSESSION WINDOW
WINDOW STARTS |  | 2026-10-16 |  | DURATION |  | 48 |  | UNIT |  | hours | WINDOW ENDS |  |  |  |  | hours
GANTT STARTS |  |  |  | GANTT SPAN |  | 48 |  | UNIT |  | hours | ONE COLUMN = |  |  |  |  | days
TOTAL HOURS |  |  |  | ELAPSED | [5 empty] | LOCATIONS |  | 5 | ACTIVITIES | 26
The Gantt is always 48 columns wide - a shorter span gives finer columns. Delivered with 5 locations x 26 activities per location; blank an ACTIVITY name to switch that row off.
LOCATIONS
No | LOCATION NAME | [6 empty] | SCOPE / SUB-TITLE SHOWN ON THE PAGE
1 | C263 – KM 209+025 | [6 empty] | 1 cell │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29
2 | C265 – KM 210+525 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29
3 | C267 – KM 212+400 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ TSO OTMP from Station 29
4 | C288 – KM 337+391 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ SABATCO OTMP from Station 35
5 | C289 – KM 338+491 | [6 empty] | 3 cells │ Main Line 1 & Main Line 3 │ SABATCO OTMP from Station 35
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
| OTMP moves from station 29 to Main Line 1 |  |  | 1 | 0 | FS | 0
| Track removal & panel evacuation (Line 1) |  |  | 1 | 1 | FS | 0
| Track removal & panel evacuation (Line 3) |  |  | 1 | 1 | SS | 0
| Ballast removal |  |  | 1 | 3 | FS | 0
| Cutting & removal around existing culvert |  |  | 3 | 4 | FS | 0
| Demolition of existing culvert |  |  | 4 | 5 | FS | 0
| Surface preparation for precast installation |  |  | 2 | 6 | FS | 0
| Installation of new precast culvert |  |  | 5 | 7 | FS | 0
| Apply sealant to the culvert |  |  | 2 | 8 | FS | 0
| Backfill around culvert to subgrade level |  |  | 5 | 9 | FS | 0
| Backfill Subgrade |  |  | 2 | 10 | FS | 0
| First layer of ballast (Line 1) |  |  | 1 | 11 | FS | 0
| First layer of ballast (Line 3) |  |  | 1 | 12 | FS | 0
| Track installation (Line 1) |  |  | 1 | 13 | FS | 0
| Track installation (Line 3) |  |  | 1 | 14 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 15 | FS | 0
| Final Ballasting / Tamping (Line 1) |  |  | 1 | 16 | FS | 0
| OTMP moves from line 1 to Line 3 TK 121+000 |  |  | 1 | 17 | FS | 0
| ATW – 2U (out of destressing) (Line 1) |  |  | 2 | 18 | FS | 0
| ATW – 2U (out of destressing) (Line 3) |  |  | 2 | 19 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 3) |  |  | 1 | 20 | FS | 0
| Final Ballasting / Tamping (Line 3) |  |  | 1 | 21 | FS | 0
| OTMP back towards station 29 |  |  | 2 | 22 | FS | 0
| Destressing (incl. 2 ATW) (Line 1) |  |  | 4 | 23 | FS | 0
| Destressing (incl. 2 ATW) (Line 3) |  |  | 4 | 24 | FS | 0
| Finishing (grinding, stamp, UT, inspection) |  |  | 1 | 25 | FS | 0
TOT
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
| OTMP moves from station 29 to Main Line 1 |  |  | 1 | 0 | FS | 0
| Track removal & panel evacuation (Line 1) |  |  | 1 | 1 | FS | 0
| Track removal & panel evacuation (Line 3) |  |  | 1 | 1 | SS | 0
| Ballast removal |  |  | 1 | 3 | FS | 0
| Cutting & removal around existing culvert |  |  | 2 | 4 | FS | 0
| Demolition of existing culvert |  |  | 2 | 5 | FS | 0
| Surface preparation for precast installation |  |  | 2 | 6 | FS | 0
| Installation of new precast culvert |  |  | 3 | 7 | FS | 0
| Apply sealant to the culvert |  |  | 1 | 8 | FS | 0
| Backfill around culvert to subgrade level |  |  | 3 | 9 | FS | 0
| Backfill Subgrade |  |  | 1 | 10 | FS | 0
| First layer of ballast (Line 1) |  |  | 1 | 11 | FS | 0
| First layer of ballast (Line 3) |  |  | 1 | 12 | FS | 0
| Track installation (Line 1) |  |  | 1 | 13 | FS | 0
| Track installation (Line 3) |  |  | 1 | 14 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 15 | FS | 0
| Final Ballasting / Tamping (Line 1) |  |  | 1 | 16 | FS | 0
| OTMP moves from line 1 to Line 3 TK 121+000 |  |  | 1 | 17 | FS | 0
| ATW – 2U (out of destressing) (Line 1) |  |  | 2 | 18 | FS | 0
| ATW – 2U (out of destressing) (Line 3) |  |  | 2 | 19 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 20 | FS | 0
| Final Ballasting / Tamping (Line 3) |  |  | 1 | 21 | FS | 0
| OTMP back towards station 29 |  |  | 2 | 22 | FS | 0
| Destressing (incl. 2 ATW) (Line 1) |  |  | 4 | 23 | FS | 0
| Destressing (incl. 2 ATW) (Line 3) |  |  | 4 | 24 | FS | 0
| Finishing (grinding, stamp, UT, inspection) |  |  | 7 | 25 | FS | 0
TOT
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
| OTMP moves from station 29 to main Line 1 |  |  | 1 | 0 | FS | 0
| Track removal & panel evacuation (Line 1) |  |  | 1 | 1 | FS | 0
| Track removal & panel evacuation (Line 3) |  |  | 1 | 1 | SS | 0
| Ballast removal |  |  | 1 | 3 | FS | 0
| Cutting & removal around existing culvert |  |  | 1 | 4 | FS | 0
| Demolition of existing culvert |  |  | 2 | 5 | FS | 0
| Surface preparation for precast installation |  |  | 2 | 6 | FS | 0
| Installation of new precast culvert |  |  | 3 | 7 | FS | 0
| Apply sealant to the culvert |  |  | 1 | 8 | FS | 0
| Backfill around culvert to subgrade level |  |  | 3 | 9 | FS | 0
| Backfill Subgrade |  |  | 1 | 10 | FS | 0
| First layer of ballast (Line 1) |  |  | 1 | 11 | FS | 0
| First layer of ballast (Line 3) |  |  | 1 | 12 | FS | 0
| Track installation (Line 1) |  |  | 1 | 13 | FS | 0
| Track installation (Line 3) |  |  | 1 | 14 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 15 | FS | 0
| Final Ballasting / Tamping (Line 1) |  |  | 1 | 16 | FS | 0
| OTMP moves from line 1 to Line 3 |  |  | 1 | 17 | FS | 0
| ATW – 4U (out of destressing) (Line 1) |  |  | 2 | 18 | FS | 0
| ATW – 4U (out of destressing) (Line 3) |  |  | 2 | 19 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 3) |  |  | 1 | 20 | FS | 0
| Final Ballasting / Tamping (Line 3) |  |  | 1 | 21 | FS | 0
| OTMP back towards station 29 |  |  | 2 | 22 | FS | 0
| Destressing (incl. 2 ATW) (Line 1) |  |  | 4 | 23 | FS | 0
| Destressing (incl. 2 ATW) (Line 3) |  |  | 4 | 24 | FS | 0
| Finishing (grinding, stamp, UT, inspection) |  |  | 1 | 25 | FS | 0
TOT
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
| OTMP moves from station 35 to main Line 1 |  |  | 1 | 0 | FS | 0
| Track removal & panel evacuation (Line 1) |  |  | 1 | 1 | FS | 0
| Track removal & panel evacuation (Line 2) |  |  | 1 | 2 | FS | 0
| Ballast removal |  |  | 1 | 3 | FS | 0
| Cutting & removal around existing culvert |  |  | 1 | 4 | FS | 0
| Demolition of existing culvert |  |  | 2 | 5 | FS | 0
| Surface preparation for precast installation |  |  | 2 | 6 | FS | 0
| Installation of new precast culvert |  |  | 3 | 7 | FS | 0
| Apply sealant to the culvert |  |  | 2 | 8 | FS | 0
| Backfill around culvert to subgrade level |  |  | 3 | 9 | FS | 0
| Backfill Subgrade |  |  | 2 | 10 | FS | 0
| First layer of ballast (Line 1) |  |  | 1 | 11 | FS | 0
| First layer of ballast (Line 3) |  |  | 1 | 12 | FS | 0
| Track installation (Line 1) |  |  | 1 | 13 | FS | 0
| Track installation (Line 3) |  |  | 1 | 14 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 15 | FS | 0
| Final Ballasting / Tamping (Line 1) |  |  | 1 | 16 | FS | 0
| OTMP moves from line 1 to line 3 (passing by Station 33) |  |  | 2 | 17 | FS | 0
| ATW – 2U (out of destressing) (Line 1) |  |  | 2 | 18 | FS | 0
| ATW – 2U (out of destressing) (Line 3) |  |  | 2 | 19 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 3) |  |  | 1 | 20 | FS | 0
| Final Ballasting / Tamping (Line 3) |  |  | 1 | 21 | FS | 0
| OTMP Back towards station 35 |  |  | 2 | 22 | FS | 0
| Destressing (incl. 2 ATW) (Line 1) |  |  | 4 | 23 | FS | 0
| Destressing (incl. 2 ATW) (Line 3) |  |  | 4 | 24 | FS | 0
| Finishing (grinding, stamp, UT, inspection) |  |  | 4 | 25 | FS | 0
TOT
No | ACTIVITY (leave blank to switch the row off) | Planned Start | Planned Finish | DUR (h) | PRED No | REL | LAG (h) | ACT START Date | ACT START Time | ACT FINISH Date | ACT FINISH Time | ACT Dur | % COMP | STATUS (auto) | REMARKS
| OTMP moves from station 35 to main Line 1 |  |  | 1 | 0 | FS | 0
| Track removal & panel evacuation (Line 1) |  |  | 1 | 1 | FS | 0
| Track removal & panel evacuation (Line 3) |  |  | 1 | 1 | SS | 0
| Ballast removal |  |  | 1 | 3 | FS | 0
| Cutting & removal around existing culvert |  |  | 2 | 4 | FS | 0
| Demolition of existing culvert |  |  | 4 | 5 | FS | 0
| Surface preparation for precast installation |  |  | 2 | 6 | FS | 0
| Installation of new precast culvert |  |  | 2 | 7 | FS | 0
| Apply sealant to the culvert |  |  | 2 | 8 | FS | 0
| Backfill around culvert to subgrade level |  |  | 5 | 9 | FS | 0
| Backfill Subgrade |  |  | 2 | 10 | FS | 0
| First layer of ballast (Line 1) |  |  | 1 | 11 | FS | 0
| First layer of ballast (Line 3) |  |  | 1 | 12 | FS | 0
| Track installation (Line 1) |  |  | 1 | 13 | FS | 0
| Track installation (Line 3) |  |  | 1 | 14 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 1) |  |  | 1 | 15 | FS | 0
| Final Ballasting / Tamping (Line 1) |  |  | 1 | 16 | FS | 0
| OTMP moves from line 1 to line 3 (passing by Station 33) |  |  | 2 | 17 | FS | 0
| ATW – 2U (out of destressing) (Line 1) |  |  | 2 | 18 | FS | 0
| ATW – 2U (out of destressing) (Line 3) |  |  | 2 | 19 | FS | 0
| 1st & 2nd Ballasting / Tamping (Line 3) |  |  | 1 | 20 | FS | 0
| Final Ballasting / Tamping (Line 3) |  |  | 1 | 21 | FS | 0
| OTMP Back towards station 35 |  |  | 2 | 22 | FS | 0
| Destressing (incl. 2 ATW) (Line 1) |  |  | 4 | 23 | FS | 0
| Destressing (incl. 2 ATW) (Line 3) |  |  | 4 | 24 | FS | 0
| Finishing (grinding, stamp, UT, inspection) |  |  | 4 | 25 | FS | 0
TOT
Note on C4: PROJECT NAME The project name printed across the top of every page of the report. Type it exactly as it should appear.
Note on K4: REPORT TITLE The large title on the cover page. Leave as 'POSSESSION PROGRESS REPORT - PLANNED vs ACTUAL' unless the report is renamed.
Note on C5: SUBTITLE One short line under the title, e.g. the type of work and the shutdown number.
Note on I5: PREPARED BY The team or person issuing the report. Printed on the cover.
Note on M5: REPORT CUT-OFF (the data date) The moment the progress in this sheet is true as of. Everything - Plan %, forecast, the black line on the Gantt - is measured from here. =NOW() keeps it live. To freeze a report, type the date and time instead, e.g. 16/10/2026 06:00
Note on C8: WINDOW STARTS Date and time the possession begins. Type both together, e.g. 16/10/2026 00:00 Every planned date in the tracker is built forward from this.
Note on G8: DURATION How long the possession lasts, in the unit chosen in the next cell. 48 hours here.
Note on K8: UNIT Choose hours or days from the list. It applies to the DURATION cell on its left.
Note on C9: GANTT STARTS Where the left edge of the Gantt begins. Normally the same as the possession start. Set it later to zoom into a window, e.g. the next 12 hours.
Note on G9: GANTT SPAN How many hours the whole Gantt covers. The Gantt is always 48 columns wide, so a smaller span gives finer columns: 48 h = 1 hour per column, 24 h = 30 min per column.
Note on K9: UNIT Choose hours or days. Applies to GANTT SPAN.
Note on M10: LOCATIONS How many culverts this tracker covers. Calculated from the blocks below - do not type over it.
Note on O10: ACTIVITIES How many activity rows each location has. To use fewer, blank the ACTIVITY name on the rows you do not need - the row switches itself off everywhere.
Note on B15: LOCATION NAME The culvert name as it should read on the cover and at the top of its own page, e.g. C263 - KM 209+025
Note on I15: SCOPE / SUB-TITLE The short line shown under the location title: number of cells, the lines affected and which OTMP serves it.
Note on B16: LOCATION NAME The culvert name as it should read on the cover and at the top of its own page, e.g. C263 - KM 209+025
Note on I16: SCOPE / SUB-TITLE The short line shown under the location title: number of cells, the lines affected and which OTMP serves it.
Note on B17: LOCATION NAME The culvert name as it should read on the cover and at the top of its own page, e.g. C263 - KM 209+025
Note on I17: SCOPE / SUB-TITLE The short line shown under the location title: number of cells, the lines affected and which OTMP serves it.
Note on B18: LOCATION NAME The culvert name as it should read on the cover and at the top of its own page, e.g. C263 - KM 209+025
Note on I18: SCOPE / SUB-TITLE The short line shown under the location title: number of cells, the lines affected and which OTMP serves it.
Note on B19: LOCATION NAME The culvert name as it should read on the cover and at the top of its own page, e.g. C263 - KM 209+025
Note on I19: SCOPE / SUB-TITLE The short line shown under the location title: number of cells, the lines affected and which OTMP serves it.
Note on A26: No The activity number. Calculated - it disappears when the ACTIVITY name next to it is blank.
Note on B26: ACTIVITY The work description shown on the report. Leave it BLANK to switch the whole row off - the row then vanishes from the tracker, the Gantt and the totals.
Note on C26: Planned Start Calculated from the link you set in PRED No / REL / LAG. Do not type here. If a date looks wrong, fix the link, not the date.
Note on D26: Planned Finish Calculated: Planned Start + DUR. Do not type here.
Note on E26: DUR (h) How many hours this activity is planned to take. Decimals are fine: 1.5 means one hour thirty.
Note on F26: PRED No The activity number THIS one follows, within this location. 0 means it starts at the possession start. 3 means it is driven by activity 3 above. It must point UPWARDS - a row cannot follow itself or a row below it, or the status reads ! CHECK LINK.
Note on G26: REL How this activity is tied to its predecessor: FS finish-to-start - starts when the other finishes (the normal one) SS start-to-start - both start together FF finish-to-finish - both finish together SF start-to-finish
Note on H26: LAG (h) Extra waiting time on the link, in hours. 0 = no wait. 2 = start two hours after. -1 = start one hour early (overlap).
Note on I26: ACT START - Date The DATE work actually started. Date only. Example: 16/10/2026 The time goes in the next cell.
Note on J26: ACT START - Time The TIME work actually started. Time only, 24-hour clock. Example: 05:30 Leave blank and it is treated as 00:00.
Note on K26: ACT FINISH - Date The DATE work actually finished. Date only. Example: 16/10/2026 Fill it in only when the activity is genuinely complete - entering a finish sets the activity to 100%.
Note on L26: ACT FINISH - Time The TIME work actually finished. Time only. Example: 14:00
Note on M26: ACT Dur Calculated: how long the activity actually took, once both the actual start and finish are entered.
Note on N26: % COMP How much of the activity is done, for work still in progress. Type 45% (or 0.45). Leave blank if nothing has started. You do not need it once an ACT FINISH is entered - that forces 100%.
Note on O26: STATUS (auto) Calculated from the dates you entered. Never type here. ! CHECK DATES means a finish is before its start, or a start is before the possession began. ! CHECK LINK means PRED No points at this row or a row below it.
Note on P26: REMARKS Free text - the reason for a delay, who is on site, what is waiting. It is for the record; it does not affect any calculation.
Note on A56: No The activity number. Calculated - it disappears when the ACTIVITY name next to it is blank.
Note on B56: ACTIVITY The work description shown on the report. Leave it BLANK to switch the whole row off - the row then vanishes from the tracker, the Gantt and the totals.
Note on C56: Planned Start Calculated from the link you set in PRED No / REL / LAG. Do not type here. If a date looks wrong, fix the link, not the date.
Note on D56: Planned Finish Calculated: Planned Start + DUR. Do not type here.
Note on E56: DUR (h) How many hours this activity is planned to take. Decimals are fine: 1.5 means one hour thirty.
Note on F56: PRED No The activity number THIS one follows, within this location. 0 means it starts at the possession start. 3 means it is driven by activity 3 above. It must point UPWARDS - a row cannot follow itself or a row below it, or the status reads ! CHECK LINK.
Note on G56: REL How this activity is tied to its predecessor: FS finish-to-start - starts when the other finishes (the normal one) SS start-to-start - both start together FF finish-to-finish - both finish together SF start-to-finish
Note on H56: LAG (h) Extra waiting time on the link, in hours. 0 = no wait. 2 = start two hours after. -1 = start one hour early (overlap).
Note on I56: ACT START - Date The DATE work actually started. Date only. Example: 16/10/2026 The time goes in the next cell.
Note on J56: ACT START - Time The TIME work actually started. Time only, 24-hour clock. Example: 05:30 Leave blank and it is treated as 00:00.
Note on K56: ACT FINISH - Date The DATE work actually finished. Date only. Example: 16/10/2026 Fill it in only when the activity is genuinely complete - entering a finish sets the activity to 100%.
Note on L56: ACT FINISH - Time The TIME work actually finished. Time only. Example: 14:00
Note on M56: ACT Dur Calculated: how long the activity actually took, once both the actual start and finish are entered.
Note on N56: % COMP How much of the activity is done, for work still in progress. Type 45% (or 0.45). Leave blank if nothing has started. You do not need it once an ACT FINISH is entered - that forces 100%.
Note on O56: STATUS (auto) Calculated from the dates you entered. Never type here. ! CHECK DATES means a finish is before its start, or a start is before the possession began. ! CHECK LINK means PRED No points at this row or a row below it.
Note on P56: REMARKS Free text - the reason for a delay, who is on site, what is waiting. It is for the record; it does not affect any calculation.
Note on A86: No The activity number. Calculated - it disappears when the ACTIVITY name next to it is blank.
Note on B86: ACTIVITY The work description shown on the report. Leave it BLANK to switch the whole row off - the row then vanishes from the tracker, the Gantt and the totals.
Note on C86: Planned Start Calculated from the link you set in PRED No / REL / LAG. Do not type here. If a date looks wrong, fix the link, not the date.
Note on D86: Planned Finish Calculated: Planned Start + DUR. Do not type here.
Note on E86: DUR (h) How many hours this activity is planned to take. Decimals are fine: 1.5 means one hour thirty.
Note on F86: PRED No The activity number THIS one follows, within this location. 0 means it starts at the possession start. 3 means it is driven by activity 3 above. It must point UPWARDS - a row cannot follow itself or a row below it, or the status reads ! CHECK LINK.
Note on G86: REL How this activity is tied to its predecessor: FS finish-to-start - starts when the other finishes (the normal one) SS start-to-start - both start together FF finish-to-finish - both finish together SF start-to-finish
Note on H86: LAG (h) Extra waiting time on the link, in hours. 0 = no wait. 2 = start two hours after. -1 = start one hour early (overlap).
Note on I86: ACT START - Date The DATE work actually started. Date only. Example: 16/10/2026 The time goes in the next cell.
Note on J86: ACT START - Time The TIME work actually started. Time only, 24-hour clock. Example: 05:30 Leave blank and it is treated as 00:00.
Note on K86: ACT FINISH - Date The DATE work actually finished. Date only. Example: 16/10/2026 Fill it in only when the activity is genuinely complete - entering a finish sets the activity to 100%.
Note on L86: ACT FINISH - Time The TIME work actually finished. Time only. Example: 14:00
Note on M86: ACT Dur Calculated: how long the activity actually took, once both the actual start and finish are entered.
Note on N86: % COMP How much of the activity is done, for work still in progress. Type 45% (or 0.45). Leave blank if nothing has started. You do not need it once an ACT FINISH is entered - that forces 100%.
Note on O86: STATUS (auto) Calculated from the dates you entered. Never type here. ! CHECK DATES means a finish is before its start, or a start is before the possession began. ! CHECK LINK means PRED No points at this row or a row below it.
Note on P86: REMARKS Free text - the reason for a delay, who is on site, what is waiting. It is for the record; it does not affect any calculation.
Note on A116: No The activity number. Calculated - it disappears when the ACTIVITY name next to it is blank.
Note on B116: ACTIVITY The work description shown on the report. Leave it BLANK to switch the whole row off - the row then vanishes from the tracker, the Gantt and the totals.
Note on C116: Planned Start Calculated from the link you set in PRED No / REL / LAG. Do not type here. If a date looks wrong, fix the link, not the date.
Note on D116: Planned Finish Calculated: Planned Start + DUR. Do not type here.
Note on E116: DUR (h) How many hours this activity is planned to take. Decimals are fine: 1.5 means one hour thirty.
Note on F116: PRED No The activity number THIS one follows, within this location. 0 means it starts at the possession start. 3 means it is driven by activity 3 above. It must point UPWARDS - a row cannot follow itself or a row below it, or the status reads ! CHECK LINK.
Note on G116: REL How this activity is tied to its predecessor: FS finish-to-start - starts when the other finishes (the normal one) SS start-to-start - both start together FF finish-to-finish - both finish together SF start-to-finish
Note on H116: LAG (h) Extra waiting time on the link, in hours. 0 = no wait. 2 = start two hours after. -1 = start one hour early (overlap).
Note on I116: ACT START - Date The DATE work actually started. Date only. Example: 16/10/2026 The time goes in the next cell.
Note on J116: ACT START - Time The TIME work actually started. Time only, 24-hour clock. Example: 05:30 Leave blank and it is treated as 00:00.
Note on K116: ACT FINISH - Date The DATE work actually finished. Date only. Example: 16/10/2026 Fill it in only when the activity is genuinely complete - entering a finish sets the activity to 100%.
Note on L116: ACT FINISH - Time The TIME work actually finished. Time only. Example: 14:00
Note on M116: ACT Dur Calculated: how long the activity actually took, once both the actual start and finish are entered.
Note on N116: % COMP How much of the activity is done, for work still in progress. Type 45% (or 0.45). Leave blank if nothing has started. You do not need it once an ACT FINISH is entered - that forces 100%.
Note on O116: STATUS (auto) Calculated from the dates you entered. Never type here. ! CHECK DATES means a finish is before its start, or a start is before the possession began. ! CHECK LINK means PRED No points at this row or a row below it.
Note on P116: REMARKS Free text - the reason for a delay, who is on site, what is waiting. It is for the record; it does not affect any calculation.
Note on A146: No The activity number. Calculated - it disappears when the ACTIVITY name next to it is blank.
Note on B146: ACTIVITY The work description shown on the report. Leave it BLANK to switch the whole row off - the row then vanishes from the tracker, the Gantt and the totals.
Note on C146: Planned Start Calculated from the link you set in PRED No / REL / LAG. Do not type here. If a date looks wrong, fix the link, not the date.
Note on D146: Planned Finish Calculated: Planned Start + DUR. Do not type here.
Note on E146: DUR (h) How many hours this activity is planned to take. Decimals are fine: 1.5 means one hour thirty.
Note on F146: PRED No The activity number THIS one follows, within this location. 0 means it starts at the possession start. 3 means it is driven by activity 3 above. It must point UPWARDS - a row cannot follow itself or a row below it, or the status reads ! CHECK LINK.
Note on G146: REL How this activity is tied to its predecessor: FS finish-to-start - starts when the other finishes (the normal one) SS start-to-start - both start together FF finish-to-finish - both finish together SF start-to-finish
Note on H146: LAG (h) Extra waiting time on the link, in hours. 0 = no wait. 2 = start two hours after. -1 = start one hour early (overlap).
Note on I146: ACT START - Date The DATE work actually started. Date only. Example: 16/10/2026 The time goes in the next cell.
Note on J146: ACT START - Time The TIME work actually started. Time only, 24-hour clock. Example: 05:30 Leave blank and it is treated as 00:00.
Note on K146: ACT FINISH - Date The DATE work actually finished. Date only. Example: 16/10/2026 Fill it in only when the activity is genuinely complete - entering a finish sets the activity to 100%.
Note on L146: ACT FINISH - Time The TIME work actually finished. Time only. Example: 14:00
Note on M146: ACT Dur Calculated: how long the activity actually took, once both the actual start and finish are entered.
Note on N146: % COMP How much of the activity is done, for work still in progress. Type 45% (or 0.45). Leave blank if nothing has started. You do not need it once an ACT FINISH is entered - that forces 100%.
Note on O146: STATUS (auto) Calculated from the dates you entered. Never type here. ! CHECK DATES means a finish is before its start, or a start is before the possession began. ! CHECK LINK means PRED No points at this row or a row below it.
Note on P146: REMARKS Free text - the reason for a delay, who is on site, what is waiting. It is for the record; it does not affect any calculation.